## budget status
| budget | hrs | Jan-June 14 | hrs | July-Aug 14 | hrs
Grant Management and Project Oversight | 1800 | 30 | 525 | 8.75 | 120 | 8.75
Task 1 Outreach to Schools | 988 | 21 | 701 | 12.25 | 0 | 12.25
Task 2 Develop Marketing Materials | 292 | 6
Task 3 Develop Training Materials | 1684 | 36 | 1910.75 | 39 | 0 | 39
Task 4 Develop emedia materials | 300 | 5
Task 5 Great Race and Incentives | 11006 | 972 | 328.75 | 7.25 | 4908 | 7.25
Task 6 Implementation | 1632 | 34
Task 7 Evaluation | 1372 | 24
Total Labor | 19074 |  | 3465.5 |  | 5028
Expenses
Incentives | 3000
Graphics | 1000
Printing | 500
4500
Total | 23574

## Summary of timesheets
Staff | M | T | W | TH | F |  | totals | description | mng | task 1 | task 2 | task 3 | task 4 | task 5 | task 6 | task 7
Wendi
week of July 14 | 2.5 | 0.5 |  |  |  |  | 3 | video and follow up | 1 |  |  |  |  | 2
week of July 21 |  |  |  |  | 1 |  | 1 | phone call with Gwen on Training update; review Terra Linda scope | [5 empty] | 1
week of July 28 |  |  |  | 1 |  |  | 1 | review transit toolkit | [5 empty] | 1
week of Aug 4 |  |  | 1 | 0.5 |  |  | 1.5 | organizing train the trainers training | 0.5 |  |  |  |  | 1
week of Aug 11 |  | 2 | 1 | 0.5 |  |  | 3.5 | review transit toolkit discuss training with Gwen | 0.5 |  |  |  |  | 3
week of Aug 18 | 1 | 3.5 |  |  | 0.5 |  | 5 | final review of toolkit; train the trainers; prepare presentation | [5 empty] | 5
15
[9 empty] | 2 | 0 | 0 | 0 | 0 | 13 | 0 | 0
[7 empty] | 900 |  | 120 | 0 | 0 | 0 | 0 | 780
Gwen
Week of July 7 |  | 2 |  |  |  |  | 2 | Research on Transit Race / questions for Marin Transit on "how to" use transit. | [5 empty] | 2
|  |  |  | 2 | 4 |  | 6 | Meetings and learning bus system; writing transit guide / investigating prizes. | [5 empty] | 6
week of July 14 |  |  | 1 |  |  |  | 1 | Communication with Lou and Ronny about meeting to collaborate on program development. | [5 empty] | 1
| 4 |  |  | 1 | 5 |  | 10 | Meeting and guide creation; conversations with MSEL about Pilot Program; collaboration with Lou | [5 empty] | 10
Week of July 21 |  |  |  | 1 | 2.5 |  | 3.5 | Update on transit guide and communication with MSEL and Wendi regarding pilot program. | [5 empty] | 3.5
week of July 28 |  | 2 |  | 3 | 1 |  | 6 | Writing of Transit Guide and plan for MSEL fall rollout of Transit Program | [5 empty] | 6
week of aug 4 | 2.5 | 4 | 4 | 3 | 2 | 1 | 16.5 | Transit Guide creation | [5 empty] | 16.5
week of aug 11 |  | 1 | 8 | 2 | 8 | 2 | 21 | Transit Guide and training program | [5 empty] | 21
week of aug 18 | 3 | 7 | 0.5 | 0.5 |  |  | 11 | Tranist Guide and Traning | [5 empty] | 11
[7 empty] | 77 |  | 0 | 0 | 0 | 0 | 0 | 77 | 0 | 0
[7 empty] | 3311 |  | 0 | 0 | 0 | 0 | 0 | 3311 | 0 | 0
Lou Goodwin
Week of July 7 |  |  |  | 2 | 2.5 |  | 4.5 | Meeting with Gwen going over Golden Gate Transit questions to Ronnie and discussing outline of plan. Prep for meeting with Robert and Ronnie from Marin Transit re: Transit project, rode there, discussed goals, incentives, bus routes etc... rode back to office. | [5 empty] | 4.5
Week of July 14 | 3 | [5 empty] | 3 | In office working with Gwen re: planning Scavenger hunt, meeting at TAM with Ronnie, Mark, Wendi re: film to be made by students for STAY project. | [5 empty] | 3
[5 empty] | 2 |  | 2 | Meet with Gwen to formulate plan for including SEL Terra Linda students into program. Conference call with Brendan at SEI re: TL student involvement. | [5 empty] | 2
week of Aug 11 | 4 | [5 empty] | 4 | Meet with Gwen for 1.75 hours to review and modify the Transit Toolkit, plan for coming month. Worked on my own on Solicitation letters and research for TL students Focus topic. Sent email to Robert and Ronny at Marin Transit Authority. | [5 empty] | 4
|  | 3.5 |  |  |  |  | 3.5 | emails to Marin Transit, Gwen, created a resources page for MSEL students, found pictures to use in student recruitment powerpoint. | [5 empty] | 3.5
week of aug 18 |  | 1.5 |  |  |  |  | 1.5 | Meet with Gwen to help prepare packets for Transit Training meeting today. | [5 empty] | 1.5
|  |  | 0.5 |  |  |  | 0.5 | Phone conversation with Gwen re follow-up on STAY meeting and planning next moves | [5 empty] | 0.5
[7 empty] | 19 |  | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0
[7 empty] | 817 |  | 0 | 0 | 0 | 0 | 0 | 817 | 0 | 0
[9 empty] | 2 | 0 | 0 | 0 | 0 | 109 | 0 | 0
[7 empty] | 5028 |  | 120 | 0 | 0 | 0 | 0 | 4908 | 0 | 0 | 5028

## Gwen week of July 7
MCBC/SR2S TIMESHEET
Employee: |  | Gwen Froh |  |  |  | Week Starting: |  | 2014-07-07
Signature: | [5 empty] | Week Ending: |  | 2014-07-13
Work Cat | Task | Subtask | School | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
TAM | 2E | CM |  | 0.5 |  | 0.75 |  |  |  |  | 1.25 | Communication with Staff
TAM | 2E | PD |  |  | 4.5 | [5 empty] | 4.5 | Staff retreat / brainstorming for expanding the education program.
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TOTALS |  |  |  | 0.5 | 4.5 | 0.75 | 0 | 0 | 0 | 0 | 5.75
MCBC |  |  |  | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
Program | Women on Wheels | [9 empty] | 0
Program | Women on Wheels - LCI | [9 empty] | 0
Program | Basic St Skills | [9 empty] | 0
Program | Basic St Skills - LCI | [9 empty] | 0
Program | Stay Transit |  |  |  | 2 | [5 empty] | 2 | Research on Transit Race / questions for Marin Transit on "how to" use transit.
Program | MCBC Staff meeting | [5 empty] | 2 |  |  |  | 2 | Staff meeting
Program | [10 empty] | 0
Program | 0 | [9 empty] | 0
Program | 0 | [9 empty] | 0
Program | Holiday | [6 empty] | 6 |  |  | 6 | July 4th Holiday
Program | Vacation | [9 empty] | 0
TOTALS |  |  |  | 0.5 | 6.5 | 0.75 | 2 | 6 | 0 | 0 | 15.75

## Gwen Week of July 14
MCBC/SR2S TIMESHEET
Employee: |  | Gwen Froh |  |  |  | Week Starting: |  | 2014-07-14
Signature: | [5 empty] | Week Ending: |  | 2014-07-20
Work Cat | Task | Subtask | School | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TOTALS |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MCBC |  |  |  | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
Program | Women on Wheels | [9 empty] | 0
Program | Women on Wheels - LCI | [9 empty] | 0
Program | Basic St Skills | [9 empty] | 0
Program | Basic St Skills - LCI | [9 empty] | 0
Program | Stay Transit |  |  |  |  | 1 |  |  |  |  | 1 | Communication with Lou and Ronny about meeting to collaborate on program development.
Program | 0 | [9 empty] | 0
Program | [10 empty] | 0
Program | 0 | [9 empty] | 0
Program | 0 | [9 empty] | 0
Program | Holiday | [9 empty] | 0
Program | Vacation | [9 empty] | 0
TOTALS |  |  |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1

## Gwen week of July 7 2nd
MCBC/SR2S TIMESHEET
Employee: |  | Gwen Froh |  |  |  | Week Starting: |  | 2014-07-07
Signature: | [5 empty] | Week Ending: |  | 2014-07-13
Work Cat | Task | Subtask | School | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
TAM | 2E | CM |  |  |  |  | 1 | 0.5 |  |  | 1.5 | Communication with staff
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TOTALS |  |  |  | 0 | 0 | 0 | 1 | 0.5 | 0 | 0 | 1.5
MCBC |  |  |  | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
Program | Women on Wheels | [9 empty] | 0
Program | Women on Wheels - LCI | [9 empty] | 0
Program | Basic St Skills | [9 empty] | 0
Program | Basic St Skills - LCI | [9 empty] | 0
Program | Stay Transit | [5 empty] | 2 | 4 |  |  | 6 | Meetings and learning bus system; writing transit guide / investigating prizes.
Program | MCBC | [9 empty] | 0
Program | [10 empty] | 0
Program | [10 empty] | 0
Program | [10 empty] | 0
Program | Holiday | [9 empty] | 0
Program | Vacation | [9 empty] | 0
TOTALS |  |  |  | 0 | 0 | 0 | 3 | 4.5 | 0 | 0 | 7.5

## Gwen week of July 14th 2nd
MCBC/SR2S TIMESHEET
Employee: |  | Gwen Froh |  |  |  | Week Starting: |  | 2014-07-14
Signature: | [5 empty] | Week Ending: |  | 2014-07-20
Work Cat | Task | Subtask | School | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
TAM | 2E | CM |  | 0.5 |  | 0.5 | 0.5 | 0.5 |  |  | 2 | Communication with staff
TAM | 2E | PD |  |  |  | 1 | 4 | 1 |  |  | 6 | iWalk poster design and collaboration with Lou and Laura - iWalk; communication with Active 4 Me regarding survey app.
TAM | 1A | RP |  |  |  | 0.5 | 1 |  |  |  | 1.5 | Updating MS/HS activities on report cards
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TOTALS |  |  |  | 0.5 | 0 | 2 | 5.5 | 1.5 | 0 | 0 | 9.5
MCBC |  |  |  | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
Program | Women on Wheels | [9 empty] | 0
Program | Women on Wheels - LCI | [9 empty] | 0
Program | Basic St Skills | [9 empty] | 0
Program | Basic St Skills - LCI | [9 empty] | 0
Program | Stay Transit |  |  | 4 |  |  | 1 | 5 |  |  | 10 | Meeting and guide creation; conversations with MSEL about Pilot Program; collaboration with Lou
Program | MCBC | [6 empty] | 1 |  |  | 1 | Training on Sales Force data entry with Peggy and Lou
Program | [10 empty] | 0
Program | 0 | [9 empty] | 0
Program | 0 | [9 empty] | 0
Program | Holiday | [9 empty] | 0
Program | Vacation | [9 empty] | 0
TOTALS |  |  |  | 4.5 | 0 | 2 | 6.5 | 7.5 | 0 | 0 | 20.5

## Gwen week of July 21
MCBC/SR2S TIMESHEET
Employee: |  | Gwen Froh |  |  |  | Week Starting: |  | 2014-07-21
Signature: | [5 empty] | Week Ending: |  | 2014-07-27
Work Cat | Task | Subtask | School | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
TAM | 2E | PD |  |  |  |  | 2.5 | 2 |  |  | 4.5 | Development of materials and prizes for iWalk; communication with Wendi about expansion of teen program.
TAM | 2E | CM |  |  |  |  | 0.5 | 0.5 |  |  | 1 | Communication with staff
TAM | [7 empty] | 0 |  |  | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TOTALS |  |  |  | 0 | 0 | 0 | 3 | 2.5 | 0 | 0 | 5.5
MCBC |  |  |  | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
Program | Women on Wheels | [9 empty] | 0
Program | Women on Wheels - LCI | [9 empty] | 0
Program | Basic St Skills | [9 empty] | 0
Program | Basic St Skills - LCI | [9 empty] | 0
Program | Stay Transit | [5 empty] | 1 | 2.5 |  |  | 3.5 | Update on transit guide and communication with MSEL and Wendi regarding pilot program.
Program | MCBC | [9 empty] | 0
Program | [10 empty] | 0
Program | 0 | [9 empty] | 0
Program | 0 | [9 empty] | 0
Program | Holiday | [9 empty] | 0
Program | Vacation |  |  | 6 | 6 | 6 |  |  |  |  | 18
TOTALS |  |  |  | 6 | 6 | 6 | 4 | 5 | 0 | 0 | 27

## Wendi week of July 14
MCBC/SR2S TIMESHEET
Employee: |  | Wendi Kallins |  |  |  | Week Starting: |  | 2014-07-14
Signature: |  | 0 |  |  |  | Week Ending: |  | 2014-07-20
Work Cat | Task | Subtask | School | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
TAM | 2D | CM |  | 1 | 1 | 1 | 1 | 1 |  |  | 5 | communications, emails with public and staff
TAM | 2C | MT |  | 0.5 | [6 empty] | 0.5 | follow up from retreat- type up notes, research
TAM | 2A | TP |  | 0.5 | [6 empty] | 0.5 | update issues list
TAM | 2A | CM |  | 0.25 | 1 | [5 empty] | 1.25 | discussion about future of Bike Train and setting up Tiburon Task force with Kathy Mcleod; confirming Greenbrae meeting; Tiburon Task Force
TAM | 1A | MG |  | 1 |  |  | 0.5 |  |  |  | 1.5 | meeting with Peggy on logistical processes; phone meeting with David on MTC budget
TAM | 3A |  |  | 0.75 | 0.25 | 0.25 |  |  |  |  | 1.25 | phone meeting with Kangado on possible integration with SchoolPool maps and web site.
TAM | 2D | PD |  |  | 1 | 2 |  |  |  |  | 3 | review and discuss new promotional documents;
TAM | 2E | PD |  |  |  | 1 |  |  |  |  | 1 | Phone meeting with Gwen on needs to teen program next school year
TAM | 2A | WA |  |  |  |  | 2 |  |  |  | 2 | meeting in Greenbrae with Marin General Project manager on crosswalk
TAM | 2F |  |  |  |  | 1 | 0.5 |  |  |  | 1.5 | setting up report card for 2013-14 school year
TAM | 2D | PD |  |  | 2 |  | 2 |  |  |  | 4 | review and develop materials and guidebooks for the fall, send direction to Jeremy, review team leader list;
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TOTALS |  |  |  | 4 | 5.25 | 5.25 | 6 | 1 | 0 | 0 | 21.5
MCBC |  |  |  | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
Program | Administration |  |  | 0.5 | 1 | 1.25 |  |  |  |  | 2.75 | meeting with Chris about invoice process; administration; develop future budget with raises; sales force updates
Program | Women on Wheels | [8 empty] | 0.5 | 0.5 | review layout and make corrections
Program | Contract Dev | [9 empty] | 0
Program | MCBC |  |  | 1 | [6 empty] | 1 | update bulletin; meeting with Jim
Program | Membership | [9 empty] | 0
Program | Partnership volunteer | [9 empty] | 0
Program | Tiburon | [9 empty] | 0
Program | STAY grant family biking |  |  |  |  | 0.5 |  |  |  |  | 0.5 | set up family biking eblast
Program | Stay Transit |  |  | 2.5 | 0.5 | [5 empty] | 3 | video and follow up
Program | Holiday | [9 empty] | 0
Program | Vacation | [6 empty] | 7 |  |  | 7
TOTALS |  |  |  | 8 | 6.75 | 7 | 6 | 8 | 0 | 0.5 | 36.25

## Wendi week of July 21
MCBC/SR2S TIMESHEET
Employee: |  | Wendi Kallins |  |  |  | Week Starting: |  | 2014-07-21
Signature: | [5 empty] | Week Ending: |  | 2014-07-27
Work Cat | Task | Subtask | School | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
TAM | 1A | RP |  | 0.5 |  |  |  | 1 |  |  | 1.5 | staff time cards
TAM | 2D | PD |  | 2 | 1 | [5 empty] | 3 | review and develop materials and guidebooks for the fall, send direction to Jeremy, review team leader list;
TAM | 2D | CM |  | 1 | 1 | 1 | 1 | 1 |  |  | 5 | communications, emails with public and staff
TAM | 2A | CM |  | 0.5 |  | 0 |  | 0 |  |  | 0.5 | communications with Larkspur on safety issues - traffic light at S. Elseo, blackberry bushes blocking visibility on bike path.
TAM | 1A | MG |  | 1 | 1 | 2 | 1 | 0.5 |  |  | 5.5 | develop revised budget for MTC funds; develop job descriptions for teen assistant and bi-lingual volunteer coordinator; enter new template into database
TAM | 2D | PD |  |  | 2 | 2 | 1 | 1 |  |  | 6 | Updating school web pages, add maps to Cove School , input team leaders.; developing overall program for next school year
TAM | 2F |  |  |  |  | 1 | 1 | 1 |  |  | 3 | entering surveys into database; work on wording of survey letters with Peggy and Gwen
TAM | 1F | [5 empty] | 3 |  |  |  | 3 | attended Facebook Seminar from
TAM | 2E | PD | [5 empty] | 0.5 |  |  | 0.5 | phone call with Gwen on Teen Probram
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TOTALS |  |  |  | 5 | 5 | 6 | 7 | 5 | 0 | 0 | 28
MCBC |  |  |  | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
Program | Administration |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 5 | administration, budgeting, non-tam emails;
Program | Women on Wheels |  |  | 1 | 1 |  |  | 1 |  |  | 3 | review layout and make corrections to copy; review WABA toolkit; pick out pictures
Program | Contract Dev | [9 empty] | 0
Program | MCBC | [9 empty] | 0
Program | Membership | [9 empty] | 0
Program | Partnership volunteer | [9 empty] | 0
Program | Tiburon | [9 empty] | 0
Program | STAY grant family biking | [9 empty] | 0
Program | Stay Transit | [6 empty] | 1 |  |  | 1 | phone call with Gwen on Training update; review Terra Linda scope
Program | Holiday | [9 empty] | 0
Program | Vacation | [9 empty] | 0
TOTALS |  |  |  | 7 | 7 | 7 | 8 | 8 | 0 | 0 | 37

## Lou week of July 7 2nd
MCBC/SR2S TIMESHEET
Employee: |  | Lou Goodwin |  |  |  | Week Starting: |  | 2014-07-07
Signature: | [5 empty] | Week Ending: |  | 2014-07-13
Work Cat | Task | Subtask | School | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
TAM | 2E | PD |  |  |  |  | 1.25 |  |  |  | 1.25 | Meeting With Gwen re: teen program planning for incentives and dates for events.
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TOTALS |  |  |  | 0 | 0 | 0 | 1.25 | 0 | 0 | 0 | 1.25
MCBC |  |  |  | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
Program | Women on Wheels | [9 empty] | 0
Program | Women on Wheels - LCI | [9 empty] | 0
Program | Basic St Skills | [5 empty] | 4.25 |  |  |  | 4.25 | Pick up supplies at office, review procedures and outline what I will say, drive there, set-up, check-in, attend class, bring all supplies back to office.
Program | Basic St Skills - LCI | [9 empty] | 0
Program | STAY transit | [5 empty] | 2 | 2.5 |  |  | 4.5 | Meeting with Gwen going over Golden Gate Transit questions to Ronnie and discussing outline of plan. Prep for meeting with Robert and Ronnie from Marin Transit re: Transit project, rode there, discussed goals, incentives, bus routes etc... rode back to office.
Program | STAY | [6 empty] | 0 |  |  | 0
Program | [10 empty] | 0
Program | [10 empty] | 0
Program | [10 empty] | 0
Program | Holiday | [9 empty] | 0
Program | Vacation | [9 empty] | 0
TOTALS |  |  |  | 0 | 0 | 0 | 7.5 | 2.5 | 0 | 0 | 10

## Lou week of July 14
MCBC/SR2S TIMESHEET
Employee: |  | Lou Goodwin |  |  |  | Week Starting: |  | 2014-07-14
Signature: | [5 empty] | Week Ending: |  | 2014-07-20
Work Cat | Task | Subtask | School | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
TAM | 2E | PD |  | 1 | [6 empty] | 1 | return emails to staff, brainstrorm ideas for poster for iWalk.
TAM | 2C | CM |  |  |  | 0.5 |  |  |  |  | 0.5 | Conversation and email with Peggy re: collection of data for Elementary schools
TAM | 2E | PD |  |  |  |  | 3 |  |  |  | 3 | previewing photos and ideas for iWalk poster, meet wih Gwen to design poster and email Jeremy.
TAM | 2C | SC | [5 empty] | 2 |  |  | 2 | Meet with Peggy to learn Sales Force data entry and to formulate google form to be sent to administrators
TAM | 2E | PD | [5 empty] | 1 |  |  | 1 | Meet with Peggy to learn Sales Force data entry and to formulate google form to be sent to administrators
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TOTALS |  |  |  | 1 | 0 | 0.5 | 3 | 3 | 0 | 0 | 7.5
MCBC |  |  |  | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
Program | Women on Wheels | [9 empty] | 0
Program | Women on Wheels - LCI | [9 empty] | 0
Program | Basic St Skills | [9 empty] | 0
Program | Basic St Skills - LCI | [9 empty] | 0
Program | STAY transit |  |  | 3 | [6 empty] | 3 | In office working with Gwen re: planning Scavenger hunt, meeting at TAM with Ronnie, Mark, Wendi re: film to be made by students for STAY project.
Program | STAY | [6 empty] | 2 |  |  | 2 | Meet with Gwen to formulate plan for including SEL Terra Linda students into program. Conference call with Brendan at SEI re: TL student involvement.
Program | [10 empty] | 0
Program | 0 | [9 empty] | 0
Program | 0 | [9 empty] | 0
Program | Holiday | [9 empty] | 0
Program | Vacation | [9 empty] | 0
TOTALS |  |  |  | 4 | 0 | 0.5 | 3 | 5 | 0 | 0 | 12.5

## Wendi Week of July 28
MCBC/SR2S TIMESHEET
Employee: |  | Wendi Kallins |  |  |  | Week Starting: |  | 2014-07-28
Signature: | [5 empty] | Week Ending: |  | 2014-08-03
Work Cat | Task | Subtask | School | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
TAM | 2D | CM |  | 1 | 1 | 1 | 1 |  |  |  | 4 | responding to general emails from public and staff
TAM | 2F |  |  | 2 | [6 empty] | 2 | enter sutvey data
TAM | 2D | EV |  | 1 | 1 | 1 | 1 |  |  |  | 4 | preparations for fall walk to school days,
TAM | 1A | RP |  |  | 2 |  | 1 |  |  |  | 3 | prepare invoice and reports
TAM | 1D |  |  |  |  | 1 |  |  |  |  | 1 | answer program questions from Alta
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TOTALS |  |  |  | 4 | 4 | 3 | 3 | 0 | 0 | 0 | 14
MCBC |  |  |  | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
Program | Administration |  |  | 1 | 3 | 2 | 1 |  |  |  | 7 | meeting with Dwayne and Jean on database; general admin; meeting with David and Jim; meeting with Dwayne on database
Program | Women on Wheels | [5 empty] | 1 |  |  |  | 1 | program development
Program | Contract Dev | [9 empty] | 0
Program | MCBC | [9 empty] | 0
Program | Membership | [9 empty] | 0
Program | Partnership volunteer | [9 empty] | 0
Program | Tiburon | [9 empty] | 0
Program | STAY grant family biking | [9 empty] | 0
Program | Stay Transit | [5 empty] | 1 |  |  |  | 1 | review transit toolkit
Program | Holiday | [9 empty] | 0
Program | Vacation | [6 empty] | 8 |  |  | 8
TOTALS |  |  |  | 5 | 7 | 5 | 6 | 8 | 0 | 0 | 31

## Wendi week of August 4
MCBC/SR2S TIMESHEET
Employee: |  | Wendi Kallins |  |  |  | Week Starting: |  | 2014-08-04
Signature: |  | 0 |  |  |  | Week Ending: |  | 2014-08-10
Work Cat | Task | Subtask | School | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
TAM | 3A |  |  | 1 | 1 | [5 empty] | 2 | review carpool guide and send to Jeremy
TAM | 2D | EV |  | 1 | 1 | 1 |  |  |  |  | 3 | posters and other incentives for
TAM | 2D | CM |  | 1 | 1 | 1 | 1 | 1 |  |  | 5 | responding to general emails
TAM | 1F |  |  | 1.5 |  | 0 |  |  |  |  | 1.5 | training for new blog site
TAM | 2F |  |  |  |  | 2.5 | 3.5 | 4 |  |  | 10 | enter surveys into database; develop survey reports; transfer info to report cards
TAM | 2D | WR |  |  |  |  | 1 | 1 |  |  | 2 | work with Peggy on stamps, research and select options
TAM | 2A | MT |  |  |  |  | 1 |  |  |  | 1 | help develop agenda for Hidden Valley, communications re: Kentfield task force meeting
TAM | 1A | GT | [5 empty] | 1 |  |  | 1 | webinar on Sustainable communities program
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TOTALS |  |  |  | 4.5 | 3 | 4.5 | 6.5 | 7 | 0 | 0 | 25.5
MCBC |  |  |  | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
Program | Administration |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 5 | gather numbers for Julia
Program | Women on Wheels |  |  | 1 | [6 empty] | 1 | develop Women on Wheels program proposal
Program | Contract Dev | [9 empty] | 0
Program | MCBC |  |  |  | 3 | [5 empty] | 3 | meeting with board and Jim on finances
Program | Membership | [9 empty] | 0
Program | Partnership volunteer | [9 empty] | 0
Program | Tiburon | [9 empty] | 0
Program | STAY grant family biking | [9 empty] | 0
Program | Stay Transit |  |  |  |  | 1 | 0.5 |  |  |  | 1.5 | organizing train the trainers training
Program | Holiday | [9 empty] | 0
Program | Vacation | [9 empty] | 0
TOTALS |  |  |  | 6.5 | 7 | 6.5 | 8 | 8 | 0 | 0 | 36

## Gwen week of July 28
MCBC/SR2S TIMESHEET
Employee: |  | Gwen Froh |  |  |  | Week Starting: |  | 2014-07-28
Signature: | [5 empty] | Week Ending: |  | 2014-08-03
Work Cat | Task | Subtask | School | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
TAM | 2E | PD |  |  |  | 0.5 |  |  |  |  | 0.5 | Communication with Lou; planning meetings
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TOTALS |  |  |  | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0.5
MCBC |  |  |  | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
Program | Women on Wheels | [9 empty] | 0
Program | Women on Wheels - LCI | [9 empty] | 0
Program | Basic St Skills | [9 empty] | 0
Program | Basic St Skills - LCI | [9 empty] | 0
Program | Stay Transit |  |  |  | 2 |  | 3 | 1 |  |  | 6 | Writing of Transit Guide and plan for MSEL fall rollout of Transit Program
Program | 0 | [9 empty] | 0
Program | [10 empty] | 0
Program | 0 | [9 empty] | 0
Program | 0 | [9 empty] | 0
Program | Holiday | [9 empty] | 0
Program | Vacation | [9 empty] | 0
TOTALS |  |  |  | 0 | 2 | 0.5 | 3 | 1 | 0 | 0 | 6.5

## Gwen week of August 4
MCBC/SR2S TIMESHEET
Employee: |  | Gwen Froh |  |  |  | Week Starting: |  | 2014-08-04
Signature: | [5 empty] | Week Ending: |  | 2014-08-10
Work Cat | Task | Subtask | School | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
TAM | 2E | PD |  |  |  | 0.5 |  |  |  |  | 0.5 | Collaboration with Lou on fall rollout of events: iWalk bulletin notices
TAM | 2E | CM |  |  |  |  | 0.5 |  |  |  | 0.5 | Communication with staff
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TOTALS |  |  |  | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 1
MCBC |  |  |  | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
Program | Women on Wheels | [9 empty] | 0
Program | Women on Wheels - LCI | [9 empty] | 0
Program | Basic St Skills | [9 empty] | 0
Program | Basic St Skills - LCI | [9 empty] | 0
Program | Stay Transit |  |  | 2.5 | 4 | 4 | 3 | 2 | 1 |  | 16.5 | Transit Guide creation
Program | 0 | [9 empty] | 0
Program | [10 empty] | 0
Program | 0 | [9 empty] | 0
Program | 0 | [9 empty] | 0
Program | Holiday | [9 empty] | 0
Program | Vacation | [9 empty] | 0
TOTALS |  |  |  | 2.5 | 4 | 4.5 | 3.5 | 2 | 1 | 0 | 17.5

## Gwen week of Aug 11
MCBC/SR2S TIMESHEET
Employee: |  | Gwen Froh |  |  |  | Week Starting: |  | 2014-08-11
Signature: | [5 empty] | Week Ending: |  | 2014-08-17
Work Cat | Task | Subtask | School | MON | TUE | WED | THU | FRI | 21 | SUN | TOTALS | Description of Task(s)
TAM | 2E | PD |  |  | 1 | [5 empty] | 1 | Collaboration on program development; iWalk and bulleting notices
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TOTALS |  |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
MCBC |  |  |  | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
Program | Women on Wheels | [9 empty] | 0
Program | Women on Wheels - LCI | [9 empty] | 0
Program | Basic St Skills | [9 empty] | 0
Program | Basic St Skills - LCI | [9 empty] | 0
Program | Stay Transit |  |  |  | 1 | 8 | 2 | 8 | 2 |  | 21 | Transit Guide and training program
Program | MCBC staff meeting | [5 empty] | 1.5 |  |  |  | 1.5
Program | [10 empty] | 0
Program | [10 empty] | 0
Program | [10 empty] | 0
Program | Holiday | [9 empty] | 0
Program | Vacation | [9 empty] | 0
TOTALS |  |  |  | 0 | 2 | 8 | 3.5 | 8 | 2 | 0 | 23.5

## Gwen week of Aug 18
MCBC/SR2S TIMESHEET
Employee: |  | Gwen Froh |  |  |  | Week Starting: |  | 2014-08-18
Signature: | [5 empty] | Week Ending: |  | 2014-08-24
Work Cat | Task | Subtask | School | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
TAM | 2E | PD |  |  |  | 0.5 |  |  |  |  | 0.5 | Program Development; flyers
TAM | 2E | CM |  | 0.5 |  | 0.5 | 0.5 |  |  |  | 1.5 | Communication with Staff
TAM | 2E | MT |  |  |  |  | 1.5 |  |  |  | 1.5 | Staff meeting
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TOTALS |  |  |  | 0.5 | 0 | 1 | 2 | 0 | 0 | 0 | 3.5
MCBC |  |  |  | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
Program | Women on Wheels | [9 empty] | 0
Program | Women on Wheels - LCI | [9 empty] | 0
Program | Basic St Skills | [9 empty] | 0
Program | Basic St Skills - LCI | [9 empty] | 0
Program | Stay Transit |  |  | 3 | 7 | 0.5 | 0.5 |  |  |  | 11 | Tranist Guide and Traning
Program | MCBC staff meeting | [9 empty] | 0
Program | [10 empty] | 0
Program | 0 | [9 empty] | 0
Program | 0 | [9 empty] | 0
Program | Holiday | [9 empty] | 0
Program | Vacation | [6 empty] | 6 |  |  | 6
TOTALS |  |  |  | 3.5 | 7 | 1.5 | 2.5 | 6 | 0 | 0 | 20.5

## Wendi week of Aug 11
MCBC/SR2S TIMESHEET
Employee: |  | Wendi Kallins |  |  |  | Week Starting: |  | 2014-08-11
Signature: | [5 empty] | Week Ending: |  | 2014-08-17
Work Cat | Task | Subtask | School | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
TAM | 3A |  |  |  | 1 | [5 empty] | 1 | work with Stephanie on strategies for promoting School Pool in Mill Valley
TAM | 2A | TP |  |  | 0.5 | [5 empty] | 0.5 | revise Hidden Valley issues list
TAM | 2D | CM |  |  | 1 | 1 | 1 | 1 |  |  | 4 | responding to general emails
TAM | 1A | RP |  |  | 1 | [5 empty] | 1 | staff time cards
TAM | 2A | MT |  |  | 0.5 |  |  | 3 |  |  | 3.5 | Kentfield agenda; Hidden Valley meeting
TAM | 2D | VM |  |  | 1 |  | 2 | 1 |  |  | 4 | review eblast and agenda for team leader meeting; working with Laura on planning; carpool toolkit; other preparations for the start of the school year
TAM | 2F |  |  |  |  | 2 | 2 | 4 |  |  | 8 | report cards
TAM | 1D | [5 empty] | 3 |  |  |  | 3 | creative grant reporting
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TOTALS |  |  |  | 0 | 5 | 3 | 8 | 9 | 0 | 0 | 25
MCBC |  |  |  | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
Program | Administration |  |  |  | 1 | 4 |  | 1 |  |  | 6 | administration, non TAM emails. Researching staff vacation hours; training for new timecard program; budget planning
Program | Women on Wheels | [9 empty] | 0
Program | Contract Dev | [9 empty] | 0
Program | MCBC | [5 empty] | 1.25 |  |  |  | 1.25 | staff meeting
Program | Membership | [9 empty] | 0
Program | Partnership volunteer | [9 empty] | 0
Program | Tiburon | [9 empty] | 0
Program | STAY grant family biking | [9 empty] | 0
Program | Stay Transit |  |  |  | 2 | 1 | 0.5 |  |  |  | 3.5 | review transit toolkit discuss training with Gwen
Program | Holiday | [9 empty] | 0
Program | Vacation | [9 empty] | 0
TOTALS |  |  |  | 0 | 8 | 8 | 9.75 | 10 | 0 | 0 | 35.75

## Wendi week of Aug 18
MCBC/SR2S TIMESHEET
Employee: |  | Wendi Kallins |  |  |  | Week Starting: |  | 2014-08-18
Signature: |  | 0 |  |  |  | Week Ending: |  | 2014-08-24
Work Cat | Task | Subtask | School | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
TAM | 2D | EV |  | 0.5 | 0.5 | 1 | 0.5 | 1 |  |  | 3.5 | conference call with State Health Dept on Iwalk; planning for team leader meeting; review and edit walk to school day check list and work with Laura on other materials
TAM | 2D | CM |  | 1 | 1 | 1 | 1 | 1 |  |  | 5 | responding to general emails from public and staff
TAM | 3A |  |  | 1 | 1.5 | 3 | 0.5 |  |  |  | 6 | develop principal back to school email; work with KangaDo on flyer, review carpool toolkit; Cove web site updates; send out message to principals; develop Cove back to school materials research and update principals on database
TAM | 1B |  |  | 5 | 0.5 |  |  | 0.5 |  |  | 6 | attend meeting on Transit study, meet afterwards about specific information requests; research answers to information requests.
TAM | 2C | CD |  | 0.5 | 0.25 | [5 empty] | 0.75 | review brief descriptions of new curruiculum line up. Sent out message to possible rodeo helpers
TAM | 2A | TP |  |  | 1 |  |  | 0.5 |  |  | 1.5 | travel plans on web site. Review Hidden Valley notes and issues list; provide info to SA Quality of life rep
TAM | 2A | MT |  |  |  | 2.5 |  |  |  |  | 2.5 | Kentfield Task Force meeting
TAM | 2D | PD |  |  |  |  | 3 | 1 |  |  | 4 | staff meeting plus prep - walk to school day, back to school, curriculum, type up notes. Talk to Laura about Clif kids order
TAM | 2F | [5 empty] | 0.5 | 0.5 |  |  | 1 | create list of green schools
TAM | 1A | RP | [5 empty] | 0.25 |  |  | 0.25 | staff time cards
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TOTALS |  |  |  | 8 | 4.75 | 7.5 | 5.5 | 4.75 | 0 | 0 | 30.5
MCBC |  |  |  | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
Program | Administration |  |  |  | 1 | 1 | 1.5 | 1 |  |  | 4.5 | non TAM emails; billing calls; other admin; meeting with Jim on contracts
Program | Women on Wheels | [5 empty] | 1 | 1 |  |  | 2 | call with LAB re: webinar and next steps; read article in Bicycle Retailers
Program | Contract Dev | [9 empty] | 0
Program | MCBC | [9 empty] | 0
Program | Membership | [9 empty] | 0
Program | Partnership volunteer | [9 empty] | 0
Program | Tiburon | [9 empty] | 0
Program | STAY grant family biking | [9 empty] | 0
Program | Stay Transit |  |  | 1 | 3.5 |  |  | 0.5 |  |  | 5 | final review of toolkit; train the trainers; prepare presentation
Program | Holiday | [9 empty] | 0
Program | Vacation | [9 empty] | 0
TOTALS |  |  |  | 9 | 9.25 | 8.5 | 8 | 7.25 | 0 | 0 | 42

## Lou week of Aug 11
MCBC/SR2S TIMESHEET
Employee: |  | Lou Goodwin |  |  |  | Week Starting: |  | 2014-08-11
Signature: | [5 empty] | Week Ending: |  | 2014-08-17
Work Cat | Task | Subtask | School | MON | TUE | WED | THU | FRI | 21 | SUN | TOTALS | Description of Task(s)
TAM | 2E | PD |  | 2.5 | [6 empty] | 2.5 | Reading and Responding to emails, researching start dates of schools, planning out 1st school contact.
TAM | 2E | EV |  | 1.5 | [6 empty] | 1.5 | emails to Sinaloa, Novato Police, Gwen, drafting email to announce iWalk.
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TOTALS |  |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4
MCBC |  |  |  | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
Program | Women on Wheels | [9 empty] | 0
Program | Women on Wheels - LCI | [9 empty] | 0
Program | Basic St Skills | [9 empty] | 0
Program | Basic St Skills - LCI | [9 empty] | 0
Program | STAY |  |  | 4 | [6 empty] | 4 | Meet with Gwen for 1.75 hours to review and modify the Transit Toolkit, plan for coming month. Worked on my own on Solicitation letters and research for TL students Focus topic. Sent email to Robert and Ronny at Marin Transit Authority.
Program | STAY |  |  |  | 3.5 | [5 empty] | 3.5 | emails to Marin Transit, Gwen, created a resources page for MSEL students, found pictures to use in student recruitment powerpoint.
Program | [10 empty] | 0
Program | [10 empty] | 0
Program | [10 empty] | 0
Program | Holiday | [9 empty] | 0
Program | Vacation | [9 empty] | 0
TOTALS |  |  |  | 8 | 3.5 | 0 | 0 | 0 | 0 | 0 | 11.5

## Lou week of aug 18
MCBC/SR2S TIMESHEET
Employee: |  | Lou Goodwin |  |  |  | Week Starting: |  | 2014-08-18
Signature: | [5 empty] | Week Ending: |  | 2014-08-24
Work Cat | Task | Subtask | School | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
TAM | 2E | CM |  | 0.5 | [6 empty] | 0.5 | Read and respond to emails.
TAM | 2E | CM |  |  |  | 0.5 |  |  |  |  | 0.5 | Phone conversation with Gwen re: staff meeting tomorrow, status of teen programing.
TAM | 2E | MT |  |  |  |  | 1.5 |  |  |  | 1.5 | SR2S Staff Meeting
TAM | 2E | PD |  |  |  |  | 1.5 |  |  |  | 1.5 | talk with Gwen re: giveaways for iWalk, teen program, reading and responding to emails.
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TAM | [10 empty] | 0
TOTALS |  |  |  | 0.5 | 0 | 0.5 | 3 | 0 | 0 | 0 | 4
MCBC |  |  |  | MON | TUE | WED | THU | FRI | SAT | SUN | TOTALS | Description of Task(s)
Program | Women on Wheels | [9 empty] | 0
Program | Women on Wheels - LCI | [9 empty] | 0
Program | Basic St Skills | [9 empty] | 0
Program | Basic St Skills - LCI | [9 empty] | 0
Program | STAY |  |  |  | 1.5 | [5 empty] | 1.5 | Meet with Gwen to help prepare packets for Transit Training meeting today.
Program | STAY |  |  |  |  | 0.5 |  |  |  |  | 0.5 | Phone conversation with Gwen re follow-up on STAY meeting and planning next moves
Program | [10 empty] | 0
Program | 0 | [9 empty] | 0
Program | 0 | [9 empty] | 0
Program | Holiday | [9 empty] | 0
Program | Vacation | [9 empty] | 0
TOTALS |  |  |  | 0.5 | 1.5 | 1 | 3 | 0 | 0 | 0 | 6