## Progress Report
Task	Sub	School	Hours	Description

1A	GT	*	1.00	webinar on Sustainable communities program

1A	RP	*	9.75	staff time cards
				TAM Report- updating spread sheets, instructions
				prepare invoice and reports
				staff timecards

1B	*	*	6.00	attend meeting on Transit study, meet afterwards about specific information requests; research answers to information requests.

1D	*	*	4.00	answer program questions from Alta
				creative grant reporting

1F	*	*	2.50	training for new blog site
				finailize report cards

2A	MT	*	10.50	help develop agenda for Hidden Valley, communications re: Kentfield task force meeting
				preparing for meetings for Hidden Valley, Kentfield
				Kentfield agenda; Hidden Valley meeting
				Kentfield Task Force meeting
		KT		Task Force Meeting- Kentfield

2A	TP	*	2.00	revise Hidden Valley issues list
				travel plans on web site. Review Hidden Valley notes and issues list; provide info to SA Quality of life rep

2C	CD	*	64.00	Continuing outline of K-5 comprehensive curriculum to facilitate block scheduling to increase effciency. Rough draft of 1st grade safety safari walk (non-street crossing) and partner sized vinyl mats to identify and discuss features of road design (signage .etc) and designated crossing structures (crosswalks, .etc).
				Researching transferring social media, news, and information into blog format and integration of constant contact and other media "blasts."
				Creating outline of more efficient block scheduling for the education programming in the schools. Developed alterntives to explore for each school and instrutor. Calculated efficiency based upon students hours/instructors hours/days required to travel. Created presentation for staff meeting.
				Revising outline of new K-5 comprehensive curriculum needed for efficienty education program scheduling. Reviewing Alameda K-5 curriculum. Evaluating materials costs for vinyl banners.
				review brief descriptions of new curruiculum line up. Sent out message to possible rodeo helpers
				Preparing education curriculum for 2014-15 academic year. Reworked bike rodeo to require 2 stations instead of 4 and potentially less paid instructors. Increased size of "Rules of the Road" to include up to 24 students. Folded "Cycling Circles" into "Obstacle Course" designed for up to 24 students. Added wide center lane with hazards (parked car, garbage can). Reorganized obstacles and circles to create flow of students that will not bottle-neck on teeter-totter by placing a start/stop location shortly before that feature. Created three sets of draft drawings before finding the best final design.
				Ressearch current products available and their design for chalking with sidewalk chalk. Chalk City product uses a stick with two foldable arms that hold chalk in a tube secured by rubber band material in center. Problems with hand chalkers include moving chalk as it wears down, securing chalk while maintaining ability to move it forward, and adding a weight to create solid lines over rough surface. Researched inner/outer diamter of PVC and common outer diamtere of chalk that we use. Designed a plunger stick to hold 1 piece of sidewalk chalk with a weight near the bottom to apply downward force. Outlined rainy-day back-up activities for K-3 curriculum to prevent rescheduling.
				Draft of 2014-15 handout for elementary PE teachers. Includes short description of lessons K-5 and description of new block scheduling. Lists general CA academic standards addressed, rainy-day alternatives and scheduling options. Formatted from 2013-14 elmentary teacher handout.
				Second and final draft of this years elementary handout explaining the new K-5 block scheduling. Highlighted benefits for teachers and both safety and health information for students at their school. Created a final PDF version shared with Peggy and staff for upcoming scheduling. Searched previously created listing of state education standards for K, 1, 3, and 5th grade.
				K-5 curriculum: outlining matierals needed, review current visual aides, updated and shared curriculum overview for PE teachers, started creating basic procedures for individaul lesson plans, started draft of Stop, Look and Listen rhyme visual aid banner. Additional refinement of rodeo diagrams for dual station layout, noted additional instruction time due to single lesson (instead of three). Respond to feedback from Wendi and Lou regarding K-5 lessons.
				Edited new curriculum overview for teachers. Added sentence explaining new K-5 format. Edited SLL rhyme banner. Added graphics and reformated layout. Reviewed videos collected over past months for inclusion in "Drive that Bike" PowerPoint.
				Outlined schools to approach this year for K-5 curriclum with PE teachers and how many days would be required to visit. Revised scheduling for Davidson MS to include only 6 or 6/7 classes. Reviewed Arkansas mountain bike in school program for content that could be added to our rides. Reviewed past emails and contacted staff at San Quentin regarding application for a "vendor card" to access the bike program.
				Updating "Drive that Bike" PowerPoint for new academic year. Shortening number of slides, updating images and videos. Custom editing images and videos (cropping, resizing, editing for content and quality). Including more information placing bike rules in the context of shared rules amongst all road users. Checking animations and transitions for erros. Saving as PDF for presentation in case of PowerPoint failure. Sending copy to Gwen for review and comments.

2C	CM	*	15.25	Phone calls and emails with staff and others.
				communications
				communications with staff and public
				Phone calls and emails with staff and others. Sharing expense report and timesheet.
				Communications- responding to emails
				Phone calls and emails with staff and others. .

2C	EM	*	38.50	research stamps for school events, order, proof posters
				Iwalk - give away supplies tracking
				Bike fleet summer maintenance. 10 new(used) bikes to replace the elementary fleet. Washed bikes. Stripped shifters/calbes and grips. Setup single-speed drivetrans. Aligned/replace brake pads.
				Continued ES bike fleet maintenance. Tightened/serviced cranks, cleaned drivetrains, removed stickers/tape, inventory needed parts and placed order using pricematch for lowest cost. Replaced rear deraileur and wheel. Replaced two chains. Replaced all grips. Inventory of serial numbers.
				Continued bike maintenance and relocating fleets. Replaced tires and tubes, check tires and rims for sharp spots or debris. Marked each bike with "I Stop @ Stop" stickers for identification. Delivered new ES fleet bikes to storage in Fairfax. Moved old ES fleet bikes to San Quentin. Looked for replacement canal bike. Pickup and return Uhaul truck.
				Reworked bike storage in trailer. Replaced 12 awkward metal hooks with 12 rubber bungees. Moved hooks to left side of trailer to hold pumps and other miscellaneious items. Added new bikes to fleet with rubber bungee hooks. Adapted bungees by shortening length and explored alternative hanging configurations. Continued annual maintenance. Stripped and ordered needed parts; brake pads, brake levers, calbes/housing, tires/tubes, and grips.
				Trailer maintenance and repair. Moved materials from trailer to tent. Cleaned and inspected floor-boards, sidewalls and roof. Removed trash and unused materials. Repaired leak from damaged sealant in roof panels. Refinished and repainted areas with rust. Reworked rubber hooks used to hang bicycles. Returned materials to trailer.

2C	MT	*	13.00	staff meeting
				Staff meeting with Peggy, Wendi, Gwen, Laura, and Lou.
				Staff retreat meeting with Wendi, Laura, Gwen, Peggy, Lou, and Jim. Covered education scheduling and program outlook for next year.
				All staff meeting with Wendi, Laura, Gwen, April, Alisha, Jim, April, Tom, and Andy.
				Staff meeting with Wendi, Peggy, Gwen, and Lou. Discussed plan for updating to K-5 and San Quentin (cans, bikes).

2C	SC	*	32.75	Update task list for school to contact, update calendar for 2014/15 school year.
				Scheduling- contact with schools, instructors, update calendar
				Starting to schedule the 2014-15 school year with Peggy. Discussed Davidson, Sun Valley, and Sinaloa. Email with Wendi as well regarding staff needs for Fridays and rodeos.
				recruiting rodeo helpers for the fall
				scheduling: communications with staff, school contacts, updating calendar

2D	CM	*	29.00	responding to general emails
				respond to general emails
				responding to general emails from public and staff
				communications with staff and public

2D	EV	*	44.50	preparations for fall walk to school days,
				posters and other incentives for
				spanish poster translations for iWalk
				conference call with State Health Dept on Iwalk; planning for team leader meeting; review and edit walk to school day check list and work with Laura on other materials
				Iwalk prep supplies
				iWalk - collaboration with Gwen
				RSVP calls for volunteer luncheon, nametags, Clif Kid coordination, hand stamps shipment, phone calls and emails, Sol Food order, created iWalk checklist 2014, created Bike Mobile document, carpool kit edits, meeting planning and organization, completed 35 shipping forms for Clif Kid
				Team Leader prep meeting activities, documents and supplies coordination, packed car, Trader Joe's - flowers and fruit, final RSVPs, spreadsheet updates, emails and phone calls
				Bacich ES "Bike Build" with Principal Sally Peck and teaching staff. Helped check 8 bikes built to be given to the Canal Alliance. Gave short presentation to school staff regarding the services provided by Safe Routes.

2D	MT	*	6.00	Training and planning meeting at Venetia Valley School with Torhalla Dabalos, prep and follow-up, recuited two new parent leaders

2D	PD	*	10.50	Stamp research and recommendations, placed order with Amazo for 30 kits, discussion with Wendi about projects and luncheon agenda, Clif Kid, SR2S and MCBC emails, team leader meeting planning, recruiting outreach and volunteer contact
				staff meeting plus prep - walk to school day, back to school, curriculum, type up notes. Talk to Laura about Clif kids order

2D	VM	*	35.75	review eblast and agenda for team leader meeting; working with Laura on planning; carpool toolkit; other preparations for the start of the school year
				preparations for team leader meeting
				Team Lead Meeting- shopping, prep supplies
				Team Lead Meeting- prep supplies
				Design invitation for volunteer luncheon, created agenda for Team Leader meeting, Clif Kid shipment coordination, updated master supplies list, created check-list for Team Leader luncheon, volunteer outreach, SR2S and MCBC emails, Wendi - planning discussions, checklist for luncheon, coordination activities with Jeremy, carpool toolkit, recruiting outreach, back-to-school planning
				Contact with Principals, PTA Presidents, recruit new volunteers, volunteer communications --- phone calls and emails

2D	WR	*	5.00	work with Peggy on stamps, research and select options
				work with Laura on stamps for walk and roll Wednesdays; prep for team leader meeting
				Created eblast to Team Leaders about September 10 - Walk and Roll Wednesdays start day in Marin County - school newsletter submission

2E	CM	*	3.50	Communication with staff
				Communication with staff.
				Read and respond to emails.
				Phone conversation with Gwen re: staff meeting tomorrow, status of teen programing.

2E	EV	*	1.50	emails to Sinaloa, Novato Police, Gwen, drafting email to announce iWalk.

2E	MT	*	3.00	Staff Meeting
				SR2S Staff Meeting

2E	PD	*	11.00	Communication with Lou; planning meetings
				Collaboration with Lou on fall rollout of events: iWalk bulletin notices
				Collaboration on program development; iWalk and bulleting notices
				Program Development; flyers
				Contacted schools about clubs and iWalk and dropped off posters.
				Reading and Responding to emails, researching start dates of schools, planning out 1st school contact.
				talk with Gwen re: giveaways for iWalk, teen program, reading and responding to emails.

2F	*	*	28.00	report cards
				Survey: update forms, update tracking, schedule tasks,
				Surveys- send to printer, pickup, start to sort supplies per school, plan for printing labels
				enter sutvey data
				enter surveys into database; develop survey reports; transfer info to report cards
				survey analysis
				create list of green schools
				survey prep materials

3A	*	*	10.00	review carpool guide and send to Jeremy
				meeting with new bi-lingual volunteer coordinator
				work with Stephanie on strategies for promoting School Pool in Mill Valley
				develop principal back to school email; work with KangaDo on flyer, review carpool toolkit; Cove web site updates; send out message to principals; develop Cove back to school materials research and update principals on database

			387.00	Total Hours

## 1. Labor by Staff - Untotaled
Week Of	Staff	Rate	Task	Sub	School	Hours	Description	Cost	Cost

7/27/14	Clark	$45.00	2D	CM	*	4.25	communications with staff and public	$191.25
7/27/14	Clark	$45.00	2C	SC	*	9.25	Update task list for school to contact, update calendar for 2014/15 school year.	$416.25
7/27/14	Clark	$45.00	2F	*	*	1.75	Survey: update forms, update tracking, schedule tasks,	$78.75
8/3/14	Clark	$45.00	2D	CM	*	2.25	communications with staff and public	$101.25
8/3/14	Clark	$45.00	2C	SC	*	4.50	Scheduling- contact with schools, instructors, update calendar	$202.50
8/3/14	Clark	$45.00	2C	EM	*	3.25	research stamps for school events, order, proof posters	$146.25
8/3/14	Clark	$45.00	2F	*	*	1.00	Surveys- send to printer, pickup, start to sort supplies per school, plan for printing labels	$45.00
8/3/14	Clark	$45.00	1A	RP	*	3.00	TAM Report- updating spread sheets, instructions	$135.00
8/10/14	Clark	$45.00	2C	CM	*	0.75	communications with staff and public	$33.75
8/10/14	Clark	$45.00	2C	EM	*	0.50	Iwalk - give away supplies tracking	$22.50
8/10/14	Clark	$45.00	2C	CM	*	1.00	Communications- responding to emails	$45.00
8/17/14	Clark	$45.00	2C	CM	*	4.75	communications	$213.75
8/17/14	Clark	$45.00	2C	MT	*	1.50	staff meeting	$67.50
8/17/14	Clark	$45.00	2C	SC	*	15.00	scheduling: communications with staff, school contacts, updating calendar	$675.00
8/17/14	Clark	$45.00	2F	*	*	2.25	survey prep materials	$101.25
8/17/14	Clark	$45.00	2D	EV	*	3.00	Iwalk prep supplies	$135.00
8/17/14	Clark	$45.00	2D	VM	*	1.25	Team Lead Meeting- shopping, prep supplies	$56.25
8/17/14	Clark	$45.00	2A	MT	KT	2.50	Task Force Meeting- Kentfield	$112.50
8/24/14	Clark	$45.00	2C	CM	*	0.75	communications	$33.75
8/24/14	Clark	$45.00	2C	SC	*	1.50	scheduling: communications with staff, school contacts, updating calendar	$67.50
8/24/14	Clark	$45.00	2D	EV	*	3.25	Iwalk prep supplies	$146.25
8/24/14	Clark	$45.00	2D	VM	*	2.00	Team Lead Meeting- prep supplies	$90.00
						69.25		$3,116.25	$3,116.25

7/27/14	Crawford	$31.00	2D	EV	*	1.00	spanish poster translations for iWalk	$31.00
						1.00		$31.00	$31.00

7/27/14	Froh	$43.00	2E	PD	*	0.50	Communication with Lou; planning meetings	$21.50
8/3/14	Froh	$43.00	2E	CM	*	0.50	Communication with staff	$21.50
8/3/14	Froh	$43.00	2E	PD	*	0.50	Collaboration with Lou on fall rollout of events: iWalk bulletin notices	$21.50
8/10/14	Froh	$43.00	2E	PD	*	1.00	Collaboration on program development; iWalk and bulleting notices	$43.00
8/17/14	Froh	$43.00	2E	MT	*	1.50	Staff Meeting	$64.50
8/17/14	Froh	$43.00	2E	CM	*	1.50	Communication with staff	$64.50
8/17/14	Froh	$43.00	2E	PD	*	0.50	Program Development; flyers	$21.50
8/24/14	Froh	$43.00	2E	CM	*	0.50	Communication with staff.	$21.50
8/24/14	Froh	$43.00	2E	PD	*	4.50	Contacted schools about clubs and iWalk and dropped off posters.	$193.50
						11.00		$473.00	$473.00

8/10/14	Goodwin	$31.00	2E	PD	*	2.50	Reading and Responding to emails, researching start dates of schools, planning out 1st school contact.	$77.50
8/10/14	Goodwin	$31.00	2E	EV	*	1.50	emails to Sinaloa, Novato Police, Gwen, drafting email to announce iWalk.	$46.50
8/17/14	Goodwin	$31.00	2E	MT	*	1.50	SR2S Staff Meeting	$46.50
8/17/14	Goodwin	$31.00	2E	CM	*	0.50	Read and respond to emails.	$15.50
8/17/14	Goodwin	$31.00	2E	CM	*	0.50	Phone conversation with Gwen re: staff meeting tomorrow, status of teen programing.	$15.50
8/17/14	Goodwin	$31.00	2E	PD	*	1.50	talk with Gwen re: giveaways for iWalk, teen program, reading and responding to emails.	$46.50
						8.00		$248.00	$248.00

7/27/14	Kallins	$59.50	2D	CM	*	4.00	responding to general emails from public and staff	$238.00
7/27/14	Kallins	$59.50	2F	*	*	2.00	enter sutvey data	$119.00
7/27/14	Kallins	$59.50	2D	EV	*	4.00	preparations for fall walk to school days,	$238.00
7/27/14	Kallins	$59.50	1A	RP	*	3.00	prepare invoice and reports	$178.50
7/27/14	Kallins	$59.50	1D	*	*	1.00	answer program questions from Alta	$59.50
8/3/14	Kallins	$59.50	2D	CM	*	7.00	responding to general emails	$416.50
8/3/14	Kallins	$59.50	3A	*	*	2.00	review carpool guide and send to Jeremy	$119.00
8/3/14	Kallins	$59.50	2D	EV	*	3.00	posters and other incentives for	$178.50
8/3/14	Kallins	$59.50	1F	*	*	1.50	training for new blog site	$89.25
8/3/14	Kallins	$59.50	2F	*	*	10.00	enter surveys into database; develop survey reports; transfer info to report cards	$595.00
8/3/14	Kallins	$59.50	2D	WR	*	2.00	work with Peggy on stamps, research and select options	$119.00
8/3/14	Kallins	$59.50	2A	MT	*	1.00	help develop agenda for Hidden Valley, communications re: Kentfield task force meeting	$59.50
8/3/14	Kallins	$59.50	1A	GT	*	1.00	webinar on Sustainable communities program	$59.50
8/10/14	Kallins	$59.50	2D	CM	*	4.00	responding to general emails	$238.00
8/10/14	Kallins	$59.50	2F	*	*	8.00	report cards	$476.00
8/10/14	Kallins	$59.50	1A	RP	*	1.00	staff time cards	$59.50
8/10/14	Kallins	$59.50	2D	CM	*	1.00	respond to general emails	$59.50
8/10/14	Kallins	$59.50	2D	WR	*	1.50	work with Laura on stamps for walk and roll Wednesdays; prep for team leader meeting	$89.25
8/10/14	Kallins	$59.50	3A	*	*	1.00	meeting with new bi-lingual volunteer coordinator	$59.50
8/10/14	Kallins	$59.50	2A	MT	*	1.00	preparing for meetings for Hidden Valley, Kentfield	$59.50
8/10/14	Kallins	$59.50	1A	RP	*	1.00	staff timecards	$59.50
8/10/14	Kallins	$59.50	2F	*	*	2.00	survey analysis	$119.00
8/10/14	Kallins	$59.50	2C	SC	*	0.50	recruiting rodeo helpers for the fall	$29.75
8/10/14	Kallins	$59.50	3A	*	*	1.00	work with Stephanie on strategies for promoting School Pool in Mill Valley	$59.50
8/10/14	Kallins	$59.50	2A	TP	*	0.50	revise Hidden Valley issues list	$29.75
8/10/14	Kallins	$59.50	2A	MT	*	3.50	Kentfield agenda; Hidden Valley meeting	$208.25
8/10/14	Kallins	$59.50	2D	VM	*	4.00	review eblast and agenda for team leader meeting; working with Laura on planning; carpool toolkit; other preparations for the start of the school year	$238.00
8/10/14	Kallins	$59.50	1D	*	*	3.00	creative grant reporting	$178.50
8/17/14	Kallins	$59.50	1A	RP	*	0.25	staff time cards	$14.88
8/17/14	Kallins	$59.50	2D	CM	*	5.00	responding to general emails from public and staff	$297.50
8/17/14	Kallins	$59.50	2D	EV	*	3.50	conference call with State Health Dept on Iwalk; planning for team leader meeting; review and edit walk to school day check list and work with Laura on other materials	$208.25
8/17/14	Kallins	$59.50	3A	*	*	6.00	develop principal back to school email; work with KangaDo on flyer, review carpool toolkit; Cove web site updates; send out message to principals; develop Cove back to school materials research and update principals on database	$357.00
8/17/14	Kallins	$59.50	1B	*	*	6.00	attend meeting on Transit study, meet afterwards about specific information requests; research answers to information requests.	$357.00
8/17/14	Kallins	$59.50	2C	CD	*	0.75	review brief descriptions of new curruiculum line up. Sent out message to possible rodeo helpers	$44.63
8/17/14	Kallins	$59.50	2A	TP	*	1.50	travel plans on web site. Review Hidden Valley notes and issues list; provide info to SA Quality of life rep	$89.25
8/17/14	Kallins	$59.50	2A	MT	*	2.50	Kentfield Task Force meeting	$148.75
8/17/14	Kallins	$59.50	2D	PD	*	4.00	staff meeting plus prep - walk to school day, back to school, curriculum, type up notes. Talk to Laura about Clif kids order	$238.00
8/17/14	Kallins	$59.50	2F	*	*	1.00	create list of green schools	$59.50
8/24/14	Kallins	$59.50	2D	CM	*	1.50	responding to general emails	$89.25
8/24/14	Kallins	$59.50	1A	RP	*	1.50	staff time cards	$89.25
8/24/14	Kallins	$59.50	2D	VM	*	2.00	preparations for team leader meeting	$119.00
8/24/14	Kallins	$59.50	1F	*	*	1.00	finailize report cards	$59.50
						111.00		$6,604.50	$6,604.50

8/10/14	Kelly	$43.55	2D	PD	*	6.50	Stamp research and recommendations, placed order with Amazo for 30 kits, discussion with Wendi about projects and luncheon agenda, Clif Kid, SR2S and MCBC emails, team leader meeting planning, recruiting outreach and volunteer contact	$283.08
8/10/14	Kelly	$43.55	2D	VM	*	20.00	Design invitation for volunteer luncheon, created agenda for Team Leader meeting, Clif Kid shipment coordination, updated master supplies list, created check-list for Team Leader luncheon, volunteer outreach, SR2S and MCBC emails, Wendi - planning discussions, checklist for luncheon, coordination activities with Jeremy, carpool toolkit, recruiting outreach, back-to-school planning	$871.00
8/10/14	Kelly	$43.55	2D	EV	*	1.00	iWalk - collaboration with Gwen	$43.55
8/10/14	Kelly	$43.55	2D	MT	*	6.00	Training and planning meeting at Venetia Valley School with Torhalla Dabalos, prep and follow-up, recuited two new parent leaders	$261.30
8/17/14	Kelly	$43.55	2D	EV	*	14.00	RSVP calls for volunteer luncheon, nametags, Clif Kid coordination, hand stamps shipment, phone calls and emails, Sol Food order, created iWalk checklist 2014, created Bike Mobile document, carpool kit edits, meeting planning and organization, completed 35 shipping forms for Clif Kid	$609.70
8/17/14	Kelly	$43.55	2D	VM	*	6.50	Contact with Principals, PTA Presidents, recruit new volunteers, volunteer communications --- phone calls and emails	$283.08
8/24/14	Kelly	$43.55	2D	EV	*	3.00	RSVP calls for volunteer luncheon, nametags, Clif Kid coordination, hand stamps shipment, phone calls and emails, Sol Food order, created iWalk checklist 2014, created Bike Mobile document, carpool kit edits, meeting planning and organization, completed 35 shipping forms for Clif Kid	$130.65
8/24/14	Kelly	$43.55	2D	EV	*	6.50	Team Leader prep meeting activities, documents and supplies coordination, packed car, Trader Joe's - flowers and fruit, final RSVPs, spreadsheet updates, emails and phone calls	$283.08
8/24/14	Kelly	$43.55	2D	WR	*	1.50	Created eblast to Team Leaders about September 10 - Walk and Roll Wednesdays start day in Marin County - school newsletter submission	$65.33
						65.00		$2,830.75	$2,830.75

7/27/14	Sievert	$38.35	2C	CM	*	2.00	Phone calls and emails with staff and others.	$76.70
7/27/14	Sievert	$38.35	2C	CD	*	4.00	Continuing outline of K-5 comprehensive curriculum to facilitate block scheduling to increase effciency. Rough draft of 1st grade safety safari walk (non-street crossing) and partner sized vinyl mats to identify and discuss features of road design (signage .etc) and designated crossing structures (crosswalks, .etc).	$153.40
7/27/14	Sievert	$38.35	2C	SC	*	2.00	Starting to schedule the 2014-15 school year with Peggy. Discussed Davidson, Sun Valley, and Sinaloa. Email with Wendi as well regarding staff needs for Fridays and rodeos.	$76.70
8/3/14	Sievert	$38.35	2C	CM	*	1.50	Phone calls and emails with staff and others.	$57.53
8/3/14	Sievert	$38.35	2C	MT	*	2.75	Staff meeting with Peggy, Wendi, Gwen, Laura, and Lou.	$105.46
8/3/14	Sievert	$38.35	2C	CD	*	2.00	Researching transferring social media, news, and information into blog format and integration of constant contact and other media "blasts."	$76.70
8/3/14	Sievert	$38.35	2C	EM	*	7.00	Bike fleet summer maintenance. 10 new(used) bikes to replace the elementary fleet. Washed bikes. Stripped shifters/calbes and grips. Setup single-speed drivetrans. Aligned/replace brake pads.	$268.45
8/3/14	Sievert	$38.35	2C	CD	*	6.00	Creating outline of more efficient block scheduling for the education programming in the schools. Developed alterntives to explore for each school and instrutor. Calculated efficiency based upon students hours/instructors hours/days required to travel. Created presentation for staff meeting.	$230.10
8/3/14	Sievert	$38.35	2C	MT	*	5.00	Staff retreat meeting with Wendi, Laura, Gwen, Peggy, Lou, and Jim. Covered education scheduling and program outlook for next year.	$191.75
8/3/14	Sievert	$38.35	2C	CD	*	4.00	Revising outline of new K-5 comprehensive curriculum needed for efficienty education program scheduling. Reviewing Alameda K-5 curriculum. Evaluating materials costs for vinyl banners.	$153.40
8/3/14	Sievert	$38.35	2C	EM	*	8.00	Continued ES bike fleet maintenance. Tightened/serviced cranks, cleaned drivetrains, removed stickers/tape, inventory needed parts and placed order using pricematch for lowest cost. Replaced rear deraileur and wheel. Replaced two chains. Replaced all grips. Inventory of serial numbers.	$306.80
8/10/14	Sievert	$38.35	2C	CM	*	1.50	Phone calls and emails with staff and others. Sharing expense report and timesheet.	$57.53
8/10/14	Sievert	$38.35	2C	EM	*	6.50	Continued bike maintenance and relocating fleets. Replaced tires and tubes, check tires and rims for sharp spots or debris. Marked each bike with "I Stop @ Stop" stickers for identification. Delivered new ES fleet bikes to storage in Fairfax. Moved old ES fleet bikes to San Quentin. Looked for replacement canal bike. Pickup and return Uhaul truck.	$249.28
8/10/14	Sievert	$38.35	2C	CD	*	6.75	Preparing education curriculum for 2014-15 academic year. Reworked bike rodeo to require 2 stations instead of 4 and potentially less paid instructors. Increased size of "Rules of the Road" to include up to 24 students. Folded "Cycling Circles" into "Obstacle Course" designed for up to 24 students. Added wide center lane with hazards (parked car, garbage can). Reorganized obstacles and circles to create flow of students that will not bottle-neck on teeter-totter by placing a start/stop location shortly before that feature. Created three sets of draft drawings before finding the best final design.	$258.86
8/10/14	Sievert	$38.35	2C	CD	*	7.00	Ressearch current products available and their design for chalking with sidewalk chalk. Chalk City product uses a stick with two foldable arms that hold chalk in a tube secured by rubber band material in center. Problems with hand chalkers include moving chalk as it wears down, securing chalk while maintaining ability to move it forward, and adding a weight to create solid lines over rough surface. Researched inner/outer diamter of PVC and common outer diamtere of chalk that we use. Designed a plunger stick to hold 1 piece of sidewalk chalk with a weight near the bottom to apply downward force. Outlined rainy-day back-up activities for K-3 curriculum to prevent rescheduling.	$268.45
8/10/14	Sievert	$38.35	2C	MT	*	1.50	All staff meeting with Wendi, Laura, Gwen, April, Alisha, Jim, April, Tom, and Andy.	$57.53
8/10/14	Sievert	$38.35	2C	CD	*	5.00	Draft of 2014-15 handout for elementary PE teachers. Includes short description of lessons K-5 and description of new block scheduling. Lists general CA academic standards addressed, rainy-day alternatives and scheduling options. Formatted from 2013-14 elmentary teacher handout.	$191.75
8/10/14	Sievert	$38.35	2C	EM	*	5.75	Reworked bike storage in trailer. Replaced 12 awkward metal hooks with 12 rubber bungees. Moved hooks to left side of trailer to hold pumps and other miscellaneious items. Added new bikes to fleet with rubber bungee hooks. Adapted bungees by shortening length and explored alternative hanging configurations. Continued annual maintenance. Stripped and ordered needed parts; brake pads, brake levers, calbes/housing, tires/tubes, and grips.	$220.51
8/10/14	Sievert	$38.35	2C	CD	*	5.75	Second and final draft of this years elementary handout explaining the new K-5 block scheduling. Highlighted benefits for teachers and both safety and health information for students at their school. Created a final PDF version shared with Peggy and staff for upcoming scheduling. Searched previously created listing of state education standards for K, 1, 3, and 5th grade.	$220.51
8/17/14	Sievert	$38.35	2C	CM	*	1.50	Phone calls and emails with staff and others. .	$57.53
8/17/14	Sievert	$38.35	2C	CD	*	6.50	K-5 curriculum: outlining matierals needed, review current visual aides, updated and shared curriculum overview for PE teachers, started creating basic procedures for individaul lesson plans, started draft of Stop, Look and Listen rhyme visual aid banner. Additional refinement of rodeo diagrams for dual station layout, noted additional instruction time due to single lesson (instead of three). Respond to feedback from Wendi and Lou regarding K-5 lessons.	$249.28
8/17/14	Sievert	$38.35	2D	EV	*	2.25	Bacich ES "Bike Build" with Principal Sally Peck and teaching staff. Helped check 8 bikes built to be given to the Canal Alliance. Gave short presentation to school staff regarding the services provided by Safe Routes.	$86.29
8/17/14	Sievert	$38.35	2C	CD	*	4.50	Edited new curriculum overview for teachers. Added sentence explaining new K-5 format. Edited SLL rhyme banner. Added graphics and reformated layout. Reviewed videos collected over past months for inclusion in "Drive that Bike" PowerPoint.	$172.58
8/17/14	Sievert	$38.35	2C	EM	*	7.50	Trailer maintenance and repair. Moved materials from trailer to tent. Cleaned and inspected floor-boards, sidewalls and roof. Removed trash and unused materials. Repaired leak from damaged sealant in roof panels. Refinished and repainted areas with rust. Reworked rubber hooks used to hang bicycles. Returned materials to trailer.	$287.63
8/17/14	Sievert	$38.35	2C	MT	*	2.25	Staff meeting with Wendi, Peggy, Gwen, and Lou. Discussed plan for updating to K-5 and San Quentin (cans, bikes).	$86.29
8/17/14	Sievert	$38.35	2C	CD	*	5.25	Outlined schools to approach this year for K-5 curriclum with PE teachers and how many days would be required to visit. Revised scheduling for Davidson MS to include only 6 or 6/7 classes. Reviewed Arkansas mountain bike in school program for content that could be added to our rides. Reviewed past emails and contacted staff at San Quentin regarding application for a "vendor card" to access the bike program.	$201.34
8/24/14	Sievert	$38.35	2C	CM	*	1.50	Phone calls and emails with staff and others.	$57.53
8/24/14	Sievert	$38.35	2C	CD	*	6.50	Updating "Drive that Bike" PowerPoint for new academic year. Shortening number of slides, updating images and videos. Custom editing images and videos (cropping, resizing, editing for content and quality). Including more information placing bike rules in the context of shared rules amongst all road users. Checking animations and transitions for erros. Saving as PDF for presentation in case of PowerPoint failure. Sending copy to Gwen for review and comments.	$249.28
						121.75		$4,669.11	$4,669.11

							Total Amount Due		$17,972.61

## 2. Labor by Staff - Totaled
Week Of	Staff	Rate	Task	Sub	School	Hours	Description	Cost	Cost

7/27/14	Clark	$45.00	2D	CM	*	4.25	communications with staff and public	$191.25
7/27/14	Clark	$45.00	2C	SC	*	9.25	Update task list for school to contact, update calendar for 2014/15 school year.	$416.25
7/27/14	Clark	$45.00	2F	*	*	1.75	Survey: update forms, update tracking, schedule tasks,	$78.75
8/3/14	Clark	$45.00	2D	CM	*	2.25	communications with staff and public	$101.25
8/3/14	Clark	$45.00	2C	SC	*	4.50	Scheduling- contact with schools, instructors, update calendar	$202.50
8/3/14	Clark	$45.00	2C	EM	*	3.25	research stamps for school events, order, proof posters	$146.25
8/3/14	Clark	$45.00	2F	*	*	1.00	Surveys- send to printer, pickup, start to sort supplies per school, plan for printing labels	$45.00
8/3/14	Clark	$45.00	1A	RP	*	3.00	TAM Report- updating spread sheets, instructions	$135.00
8/10/14	Clark	$45.00	2C	CM	*	.75	communications with staff and public	$33.75
8/10/14	Clark	$45.00	2C	EM	*	.50	Iwalk - give away supplies tracking	$22.50
8/10/14	Clark	$45.00	2C	CM	*	1.00	Communications- responding to emails	$45.00
8/17/14	Clark	$45.00	2C	CM	*	4.75	communications	$213.75
8/17/14	Clark	$45.00	2C	MT	*	1.50	staff meeting	$67.50
8/17/14	Clark	$45.00	2C	SC	*	15.00	scheduling: communications with staff, school contacts, updating calendar	$675.00
8/17/14	Clark	$45.00	2F	*	*	2.25	survey prep materials	$101.25
8/17/14	Clark	$45.00	2D	EV	*	3.00	Iwalk prep supplies	$135.00
8/17/14	Clark	$45.00	2D	VM	*	1.25	Team Lead Meeting- shopping, prep supplies	$56.25
8/17/14	Clark	$45.00	2A	MT	KT	2.50	Task Force Meeting- Kentfield	$112.50
8/24/14	Clark	$45.00	2C	CM	*	.75	communications	$33.75
8/24/14	Clark	$45.00	2C	SC	*	1.50	scheduling: communications with staff, school contacts, updating calendar	$67.50
8/24/14	Clark	$45.00	2D	EV	*	3.25	Iwalk prep supplies	$146.25
8/24/14	Clark	$45.00	2D	VM	*	2.00	Team Lead Meeting- prep supplies	$90.00
						69.25		$3,116.25	$3,116.25

7/27/14	Crawford	$31.00	2D	EV	*	1.00	spanish poster translations for iWalk	$31.00
						1.00		$31.00	$31.00

7/27/14	Froh	$43.00	2E	PD	*	.50	Communication with Lou; planning meetings	$21.50
8/3/14	Froh	$43.00	2E	CM	*	.50	Communication with staff	$21.50
8/3/14	Froh	$43.00	2E	PD	*	.50	Collaboration with Lou on fall rollout of events: iWalk bulletin notices	$21.50
8/10/14	Froh	$43.00	2E	PD	*	1.00	Collaboration on program development; iWalk and bulleting notices	$43.00
8/17/14	Froh	$43.00	2E	MT	*	1.50	Staff Meeting	$64.50
8/17/14	Froh	$43.00	2E	CM	*	1.50	Communication with staff	$64.50
8/17/14	Froh	$43.00	2E	PD	*	.50	Program Development; flyers	$21.50
8/24/14	Froh	$43.00	2E	CM	*	.50	Communication with staff.	$21.50
8/24/14	Froh	$43.00	2E	PD	*	4.50	Contacted schools about clubs and iWalk and dropped off posters.	$193.50
						11.00		$473.00	$473.00

8/10/14	Goodwin	$31.00	2E	PD	*	2.50	Reading and Responding to emails, researching start dates of schools, planning out 1st school contact.	$77.50
8/10/14	Goodwin	$31.00	2E	EV	*	1.50	emails to Sinaloa, Novato Police, Gwen, drafting email to announce iWalk.	$46.50
8/17/14	Goodwin	$31.00	2E	MT	*	1.50	SR2S Staff Meeting	$46.50
8/17/14	Goodwin	$31.00	2E	CM	*	.50	Read and respond to emails.	$15.50
8/17/14	Goodwin	$31.00	2E	CM	*	.50	Phone conversation with Gwen re: staff meeting tomorrow, status of teen programing.	$15.50
8/17/14	Goodwin	$31.00	2E	PD	*	1.50	talk with Gwen re: giveaways for iWalk, teen program, reading and responding to emails.	$46.50
						8.00		$248.00	$248.00

7/27/14	Kallins	$59.50	2D	CM	*	4.00	responding to general emails from public and staff	$238.00
7/27/14	Kallins	$59.50	2F	*	*	2.00	enter sutvey data	$119.00
7/27/14	Kallins	$59.50	2D	EV	*	4.00	preparations for fall walk to school days,	$238.00
7/27/14	Kallins	$59.50	1A	RP	*	3.00	prepare invoice and reports	$178.50
7/27/14	Kallins	$59.50	1D	*	*	1.00	answer program questions from Alta	$59.50
8/3/14	Kallins	$59.50	2D	CM	*	7.00	responding to general emails	$416.50
8/3/14	Kallins	$59.50	3A	*	*	2.00	review carpool guide and send to Jeremy	$119.00
8/3/14	Kallins	$59.50	2D	EV	*	3.00	posters and other incentives for	$178.50
8/3/14	Kallins	$59.50	1F	*	*	1.50	training for new blog site	$89.25
8/3/14	Kallins	$59.50	2F	*	*	10.00	enter surveys into database; develop survey reports; transfer info to report cards	$595.00
8/3/14	Kallins	$59.50	2D	WR	*	2.00	work with Peggy on stamps, research and select options	$119.00
8/3/14	Kallins	$59.50	2A	MT	*	1.00	help develop agenda for Hidden Valley, communications re: Kentfield task force meeting	$59.50
8/3/14	Kallins	$59.50	1A	GT	*	1.00	webinar on Sustainable communities program	$59.50
8/10/14	Kallins	$59.50	2D	CM	*	4.00	responding to general emails	$238.00
8/10/14	Kallins	$59.50	2F	*	*	8.00	report cards	$476.00
8/10/14	Kallins	$59.50	1A	RP	*	1.00	staff time cards	$59.50
41861	Kallins	$59.50	2D	CM	*	1.00	respond to general emails	$59.50
8/10/14	Kallins	$59.50	2D	WR	*	1.50	work with Laura on stamps for walk and roll Wednesdays; prep for team leader meeting	$89.25
8/10/14	Kallins	$59.50	3A	*	*	1.00	meeting with new bi-lingual volunteer coordinator	$59.50
8/10/14	Kallins	$59.50	2A	MT	*	1.00	preparing for meetings for Hidden Valley, Kentfield	$59.50
8/10/14	Kallins	$59.50	1A	RP	*	1.00	staff timecards	$59.50
8/10/14	Kallins	$59.50	2F	*	*	2.00	survey analysis	$119.00
8/10/14	Kallins	$59.50	2C	SC	*	.50	recruiting rodeo helpers for the fall	$29.75
8/10/14	Kallins	$59.50	3A	*	*	1.00	work with Stephanie on strategies for promoting School Pool in Mill Valley	$59.50
8/10/14	Kallins	$59.50	2A	TP	*	.50	revise Hidden Valley issues list	$29.75
8/10/14	Kallins	$59.50	2A	MT	*	3.50	Kentfield agenda; Hidden Valley meeting	$208.25
8/10/14	Kallins	$59.50	2D	VM	*	4.00	review eblast and agenda for team leader meeting; working with Laura on planning; carpool toolkit; other preparations for the start of the school year	$238.00
8/10/14	Kallins	$59.50	1D	*	*	3.00	creative grant reporting	$178.50
8/17/14	Kallins	$59.50	1A	RP	*	.25	staff time cards	$14.88
8/17/14	Kallins	$59.50	2D	CM	*	5.00	responding to general emails from public and staff	$297.50
41868	Kallins	$59.50	2D	EV	*	3.50	conference call with State Health Dept on Iwalk; planning for team leader meeting; review and edit walk to school day check list and work with Laura on other materials	$208.25
8/17/14	Kallins	$59.50	3A	*	*	6.00	develop principal back to school email; work with KangaDo on flyer, review carpool toolkit; Cove web site updates; send out message to principals; develop Cove back to school materials research and update principals on database	$357.00
8/17/14	Kallins	$59.50	1B	*	*	6.00	attend meeting on Transit study, meet afterwards about specific information requests; research answers to information requests.	$357.00
8/17/14	Kallins	$59.50	2C	CD	*	.75	review brief descriptions of new curruiculum line up. Sent out message to possible rodeo helpers	$44.63
8/17/14	Kallins	$59.50	2A	TP	*	1.50	travel plans on web site. Review Hidden Valley notes and issues list; provide info to SA Quality of life rep	$89.25
8/17/14	Kallins	$59.50	2A	MT	*	2.50	Kentfield Task Force meeting	$148.75
8/17/14	Kallins	$59.50	2D	PD	*	4.00	staff meeting plus prep - walk to school day, back to school, curriculum, type up notes. Talk to Laura about Clif kids order	$238.00
8/17/14	Kallins	$59.50	2F	*	*	1.00	create list of green schools	$59.50
8/24/14	Kallins	$59.50	2D	CM	*	1.50	responding to general emails	$89.25
8/24/14	Kallins	$59.50	1A	RP	*	1.50	staff time cards	$89.25
8/24/14	Kallins	$59.50	2D	VM	*	2.00	preparations for team leader meeting	$119.00
8/24/14	Kallins	$59.50	1F	*	*	1.00	finailize report cards	$59.50
						111.00		$6,604.50	$6,604.50

8/10/14	Kelly	$43.55	2D	PD	*	6.50	Stamp research and recommendations, placed order with Amazo for 30 kits, discussion with Wendi about projects and luncheon agenda, Clif Kid, SR2S and MCBC emails, team leader meeting planning, recruiting outreach and volunteer contact	$283.08
8/10/14	Kelly	$43.55	2D	VM	*	20.00	Design invitation for volunteer luncheon, created agenda for Team Leader meeting, Clif Kid shipment coordination, updated master supplies list, created check-list for Team Leader luncheon, volunteer outreach, SR2S and MCBC emails, Wendi - planning discussions, checklist for luncheon, coordination activities with Jeremy, carpool toolkit, recruiting outreach, back-to-school planning	$871.00
8/10/14	Kelly	$43.55	2D	EV	*	1.00	iWalk - collaboration with Gwen	$43.55
8/10/14	Kelly	$43.55	2D	MT	*	6.00	Training and planning meeting at Venetia Valley School with Torhalla Dabalos, prep and follow-up, recuited two new parent leaders	$261.30
8/17/14	Kelly	$43.55	2D	EV	*	14.00	RSVP calls for volunteer luncheon, nametags, Clif Kid coordination, hand stamps shipment, phone calls and emails, Sol Food order, created iWalk checklist 2014, created Bike Mobile document, carpool kit edits, meeting planning and organization, completed 35 shipping forms for Clif Kid	$609.70
8/17/14	Kelly	$43.55	2D	VM	*	6.50	Contact with Principals, PTA Presidents, recruit new volunteers, volunteer communications --- phone calls and emails	$283.08
8/24/14	Kelly	$43.55	2D	EV	*	3.00	RSVP calls for volunteer luncheon, nametags, Clif Kid coordination, hand stamps shipment, phone calls and emails, Sol Food order, created iWalk checklist 2014, created Bike Mobile document, carpool kit edits, meeting planning and organization, completed 35 shipping forms for Clif Kid	$130.65
8/24/14	Kelly	$43.55	2D	EV	*	6.50	Team Leader prep meeting activities, documents and supplies coordination, packed car, Trader Joe's - flowers and fruit, final RSVPs, spreadsheet updates, emails and phone calls	$283.08
8/24/14	Kelly	$43.55	2D	WR	*	1.50	Created eblast to Team Leaders about September 10 - Walk and Roll Wednesdays start day in Marin County - school newsletter submission	$65.33
						65.00		$2,830.75	$2,830.75

7/27/14	Sievert	$38.35	2C	CM	*	2.00	Phone calls and emails with staff and others.	$76.70
7/27/14	Sievert	$38.35	2C	CD	*	4.00	Continuing outline of K-5 comprehensive curriculum to facilitate block scheduling to increase effciency. Rough draft of 1st grade safety safari walk (non-street crossing) and partner sized vinyl mats to identify and discuss features of road design (signage .etc) and designated crossing structures (crosswalks, .etc).	$153.40
7/27/14	Sievert	$38.35	2C	SC	*	2.00	Starting to schedule the 2014-15 school year with Peggy. Discussed Davidson, Sun Valley, and Sinaloa. Email with Wendi as well regarding staff needs for Fridays and rodeos.	$76.70
8/3/14	Sievert	$38.35	2C	CM	*	1.50	Phone calls and emails with staff and others.	$57.53
8/3/14	Sievert	$38.35	2C	MT	*	2.75	Staff meeting with Peggy, Wendi, Gwen, Laura, and Lou.	$105.46
8/3/14	Sievert	$38.35	2C	CD	*	2.00	Researching transferring social media, news, and information into blog format and integration of constant contact and other media "blasts."	$76.70
8/3/14	Sievert	$38.35	2C	EM	*	7.00	Bike fleet summer maintenance. 10 new(used) bikes to replace the elementary fleet. Washed bikes. Stripped shifters/calbes and grips. Setup single-speed drivetrans. Aligned/replace brake pads.	$268.45
8/3/14	Sievert	$38.35	2C	CD	*	6.00	Creating outline of more efficient block scheduling for the education programming in the schools. Developed alterntives to explore for each school and instrutor. Calculated efficiency based upon students hours/instructors hours/days required to travel. Created presentation for staff meeting.	$230.10
8/3/14	Sievert	$38.35	2C	MT	*	5.00	Staff retreat meeting with Wendi, Laura, Gwen, Peggy, Lou, and Jim. Covered education scheduling and program outlook for next year.	$191.75
8/3/14	Sievert	$38.35	2C	CD	*	4.00	Revising outline of new K-5 comprehensive curriculum needed for efficienty education program scheduling. Reviewing Alameda K-5 curriculum. Evaluating materials costs for vinyl banners.	$153.40
8/3/14	Sievert	$38.35	2C	EM	*	8.00	Continued ES bike fleet maintenance. Tightened/serviced cranks, cleaned drivetrains, removed stickers/tape, inventory needed parts and placed order using pricematch for lowest cost. Replaced rear deraileur and wheel. Replaced two chains. Replaced all grips. Inventory of serial numbers.	$306.80
8/10/14	Sievert	$38.35	2C	CM	*	1.50	Phone calls and emails with staff and others. Sharing expense report and timesheet.	$57.53
8/10/14	Sievert	$38.35	2C	EM	*	6.50	Continued bike maintenance and relocating fleets. Replaced tires and tubes, check tires and rims for sharp spots or debris. Marked each bike with "I Stop @ Stop" stickers for identification. Delivered new ES fleet bikes to storage in Fairfax. Moved old ES fleet bikes to San Quentin. Looked for replacement canal bike. Pickup and return Uhaul truck.	$249.28
8/10/14	Sievert	$38.35	2C	CD	*	6.75	Preparing education curriculum for 2014-15 academic year. Reworked bike rodeo to require 2 stations instead of 4 and potentially less paid instructors. Increased size of "Rules of the Road" to include up to 24 students. Folded "Cycling Circles" into "Obstacle Course" designed for up to 24 students. Added wide center lane with hazards (parked car, garbage can). Reorganized obstacles and circles to create flow of students that will not bottle-neck on teeter-totter by placing a start/stop location shortly before that feature. Created three sets of draft drawings before finding the best final design.	$258.86
8/10/14	Sievert	$38.35	2C	CD	*	7.00	Ressearch current products available and their design for chalking with sidewalk chalk. Chalk City product uses a stick with two foldable arms that hold chalk in a tube secured by rubber band material in center. Problems with hand chalkers include moving chalk as it wears down, securing chalk while maintaining ability to move it forward, and adding a weight to create solid lines over rough surface. Researched inner/outer diamter of PVC and common outer diamtere of chalk that we use. Designed a plunger stick to hold 1 piece of sidewalk chalk with a weight near the bottom to apply downward force. Outlined rainy-day back-up activities for K-3 curriculum to prevent rescheduling.	$268.45
8/10/14	Sievert	$38.35	2C	MT	*	1.50	All staff meeting with Wendi, Laura, Gwen, April, Alisha, Jim, April, Tom, and Andy.	$57.53
8/10/14	Sievert	$38.35	2C	CD	*	5.00	Draft of 2014-15 handout for elementary PE teachers. Includes short description of lessons K-5 and description of new block scheduling. Lists general CA academic standards addressed, rainy-day alternatives and scheduling options. Formatted from 2013-14 elmentary teacher handout.	$191.75
8/10/14	Sievert	$38.35	2C	EM	*	5.75	Reworked bike storage in trailer. Replaced 12 awkward metal hooks with 12 rubber bungees. Moved hooks to left side of trailer to hold pumps and other miscellaneious items. Added new bikes to fleet with rubber bungee hooks. Adapted bungees by shortening length and explored alternative hanging configurations. Continued annual maintenance. Stripped and ordered needed parts; brake pads, brake levers, calbes/housing, tires/tubes, and grips.	$220.51
8/10/14	Sievert	$38.35	2C	CD	*	5.75	Second and final draft of this years elementary handout explaining the new K-5 block scheduling. Highlighted benefits for teachers and both safety and health information for students at their school. Created a final PDF version shared with Peggy and staff for upcoming scheduling. Searched previously created listing of state education standards for K, 1, 3, and 5th grade.	$220.51
8/17/14	Sievert	$38.35	2C	CM	*	1.50	Phone calls and emails with staff and others. .	$57.53
8/17/14	Sievert	$38.35	2C	CD	*	6.50	K-5 curriculum: outlining matierals needed, review current visual aides, updated and shared curriculum overview for PE teachers, started creating basic procedures for individaul lesson plans, started draft of Stop, Look and Listen rhyme visual aid banner. Additional refinement of rodeo diagrams for dual station layout, noted additional instruction time due to single lesson (instead of three). Respond to feedback from Wendi and Lou regarding K-5 lessons.	$249.28
8/17/14	Sievert	$38.35	2D	EV	*	2.25	Bacich ES "Bike Build" with Principal Sally Peck and teaching staff. Helped check 8 bikes built to be given to the Canal Alliance. Gave short presentation to school staff regarding the services provided by Safe Routes.	$86.29
8/17/14	Sievert	$38.35	2C	CD	*	4.50	Edited new curriculum overview for teachers. Added sentence explaining new K-5 format. Edited SLL rhyme banner. Added graphics and reformated layout. Reviewed videos collected over past months for inclusion in "Drive that Bike" PowerPoint.	$172.58
8/17/14	Sievert	$38.35	2C	EM	*	7.50	Trailer maintenance and repair. Moved materials from trailer to tent. Cleaned and inspected floor-boards, sidewalls and roof. Removed trash and unused materials. Repaired leak from damaged sealant in roof panels. Refinished and repainted areas with rust. Reworked rubber hooks used to hang bicycles. Returned materials to trailer.	$287.63
8/17/14	Sievert	$38.35	2C	MT	*	2.25	Staff meeting with Wendi, Peggy, Gwen, and Lou. Discussed plan for updating to K-5 and San Quentin (cans, bikes).	$86.29
8/17/14	Sievert	$38.35	2C	CD	*	5.25	Outlined schools to approach this year for K-5 curriclum with PE teachers and how many days would be required to visit. Revised scheduling for Davidson MS to include only 6 or 6/7 classes. Reviewed Arkansas mountain bike in school program for content that could be added to our rides. Reviewed past emails and contacted staff at San Quentin regarding application for a "vendor card" to access the bike program.	$201.34
8/24/14	Sievert	$38.35	2C	CM	*	1.50	Phone calls and emails with staff and others.	$57.53
8/24/14	Sievert	$38.35	2C	CD	*	6.50	Updating "Drive that Bike" PowerPoint for new academic year. Shortening number of slides, updating images and videos. Custom editing images and videos (cropping, resizing, editing for content and quality). Including more information placing bike rules in the context of shared rules amongst all road users. Checking animations and transitions for erros. Saving as PDF for presentation in case of PowerPoint failure. Sending copy to Gwen for review and comments.	$249.28
						121.75		$4,669.11	$4,669.11

							Total Amount Due		$17,972.61

## 3. Labor by Task - Untotaled
Week Of	Staff	Rate	Task	Sub	School	Hours	Description	Cost	Cost

8/3/14	Kallins	$59.50	1A	GT	*	1.00	webinar on Sustainable communities program	$59.50		59.5
7/27/14	Kallins	$59.50	1A	RP	*	3.00	prepare invoice and reports	$178.50
8/3/14	Clark	$45.00	1A	RP	*	3.00	TAM Report- updating spread sheets, instructions	$135.00
8/10/14	Kallins	$59.50	1A	RP	*	1.00	staff time cards	$59.50
8/10/14	Kallins	$59.50	1A	RP	*	1.00	staff timecards	$59.50
8/17/14	Kallins	$59.50	1A	RP	*	.25	staff time cards	$14.88
8/24/14	Kallins	$59.50	1A	RP	*	1.50	staff time cards	$89.25	$596.13	536.625
8/17/14	Kallins	$59.50	1B	*	*	6.00	attend meeting on Transit study, meet afterwards about specific information requests; research answers to information requests.	$357.00	$357.00	357
7/27/14	Kallins	$59.50	1D	*	*	1.00	answer program questions from Alta	$59.50
8/10/14	Kallins	$59.50	1D	*	*	3.00	creative grant reporting	$178.50	$238.00	238
8/3/14	Kallins	$59.50	1F	*	*	1.50	training for new blog site	$89.25
8/24/14	Kallins	$59.50	1F	*	*	1.00	finailize report cards	$59.50	$148.75	148.75
8/3/14	Kallins	$59.50	2A	MT	*	1.00	help develop agenda for Hidden Valley, communications re: Kentfield task force meeting	$59.50
8/10/14	Kallins	$59.50	2A	MT	*	1.00	preparing for meetings for Hidden Valley, Kentfield	$59.50
8/10/14	Kallins	$59.50	2A	MT	*	3.50	Kentfield agenda; Hidden Valley meeting	$208.25
8/17/14	Kallins	$59.50	2A	MT	*	2.50	Kentfield Task Force meeting	$148.75
8/17/14	Clark	$45.00	2A	MT	KT	2.50	Task Force Meeting- Kentfield	$112.50		588.5
8/10/14	Kallins	$59.50	2A	TP	*	.50	revise Hidden Valley issues list	$29.75
8/17/14	Kallins	$59.50	2A	TP	*	1.50	travel plans on web site. Review Hidden Valley notes and issues list; provide info to SA Quality of life rep	$89.25	$707.50	119
7/27/14	Sievert	$38.35	2C	CD	*	4.00	Continuing outline of K-5 comprehensive curriculum to facilitate block scheduling to increase effciency. Rough draft of 1st grade safety safari walk (non-street crossing) and partner sized vinyl mats to identify and discuss features of road design (signage .etc) and designated crossing structures (crosswalks, .etc).	$153.40
8/3/14	Sievert	$38.35	2C	CD	*	2.00	Researching transferring social media, news, and information into blog format and integration of constant contact and other media "blasts."	$76.70
8/3/14	Sievert	$38.35	2C	CD	*	6.00	Creating outline of more efficient block scheduling for the education programming in the schools. Developed alterntives to explore for each school and instrutor. Calculated efficiency based upon students hours/instructors hours/days required to travel. Created presentation for staff meeting.	$230.10
8/3/14	Sievert	$38.35	2C	CD	*	4.00	Revising outline of new K-5 comprehensive curriculum needed for efficienty education program scheduling. Reviewing Alameda K-5 curriculum. Evaluating materials costs for vinyl banners.	$153.40
8/10/14	Sievert	$38.35	2C	CD	*	6.75	Preparing education curriculum for 2014-15 academic year. Reworked bike rodeo to require 2 stations instead of 4 and potentially less paid instructors. Increased size of "Rules of the Road" to include up to 24 students. Folded "Cycling Circles" into "Obstacle Course" designed for up to 24 students. Added wide center lane with hazards (parked car, garbage can). Reorganized obstacles and circles to create flow of students that will not bottle-neck on teeter-totter by placing a start/stop location shortly before that feature. Created three sets of draft drawings before finding the best final design.	$258.86
8/10/14	Sievert	$38.35	2C	CD	*	7.00	Ressearch current products available and their design for chalking with sidewalk chalk. Chalk City product uses a stick with two foldable arms that hold chalk in a tube secured by rubber band material in center. Problems with hand chalkers include moving chalk as it wears down, securing chalk while maintaining ability to move it forward, and adding a weight to create solid lines over rough surface. Researched inner/outer diamter of PVC and common outer diamtere of chalk that we use. Designed a plunger stick to hold 1 piece of sidewalk chalk with a weight near the bottom to apply downward force. Outlined rainy-day back-up activities for K-3 curriculum to prevent rescheduling.	$268.45
8/10/14	Sievert	$38.35	2C	CD	*	5.00	Draft of 2014-15 handout for elementary PE teachers. Includes short description of lessons K-5 and description of new block scheduling. Lists general CA academic standards addressed, rainy-day alternatives and scheduling options. Formatted from 2013-14 elmentary teacher handout.	$191.75
8/10/14	Sievert	$38.35	2C	CD	*	5.75	Second and final draft of this years elementary handout explaining the new K-5 block scheduling. Highlighted benefits for teachers and both safety and health information for students at their school. Created a final PDF version shared with Peggy and staff for upcoming scheduling. Searched previously created listing of state education standards for K, 1, 3, and 5th grade.	$220.51
8/17/14	Kallins	$59.50	2C	CD	*	.75	review brief descriptions of new curruiculum line up. Sent out message to possible rodeo helpers	$44.63
8/17/14	Sievert	$38.35	2C	CD	*	6.50	K-5 curriculum: outlining matierals needed, review current visual aides, updated and shared curriculum overview for PE teachers, started creating basic procedures for individaul lesson plans, started draft of Stop, Look and Listen rhyme visual aid banner. Additional refinement of rodeo diagrams for dual station layout, noted additional instruction time due to single lesson (instead of three). Respond to feedback from Wendi and Lou regarding K-5 lessons.	$249.28
8/17/14	Sievert	$38.35	2C	CD	*	4.50	Edited new curriculum overview for teachers. Added sentence explaining new K-5 format. Edited SLL rhyme banner. Added graphics and reformated layout. Reviewed videos collected over past months for inclusion in "Drive that Bike" PowerPoint.	$172.58
8/17/14	Sievert	$38.35	2C	CD	*	5.25	Outlined schools to approach this year for K-5 curriclum with PE teachers and how many days would be required to visit. Revised scheduling for Davidson MS to include only 6 or 6/7 classes. Reviewed Arkansas mountain bike in school program for content that could be added to our rides. Reviewed past emails and contacted staff at San Quentin regarding application for a "vendor card" to access the bike program.	$201.34
8/24/14	Sievert	$38.35	2C	CD	*	6.50	Updating "Drive that Bike" PowerPoint for new academic year. Shortening number of slides, updating images and videos. Custom editing images and videos (cropping, resizing, editing for content and quality). Including more information placing bike rules in the context of shared rules amongst all road users. Checking animations and transitions for erros. Saving as PDF for presentation in case of PowerPoint failure. Sending copy to Gwen for review and comments.	$249.28		2470.2625
7/27/14	Sievert	$38.35	2C	CM	*	2.00	Phone calls and emails with staff and others.	$76.70
8/3/14	Sievert	$38.35	2C	CM	*	1.50	Phone calls and emails with staff and others.	$57.53
8/10/14	Clark	$45.00	2C	CM	*	.75	communications with staff and public	$33.75
8/10/14	Clark	$45.00	2C	CM	*	1.00	Communications- responding to emails	$45.00
8/10/14	Sievert	$38.35	2C	CM	*	1.50	Phone calls and emails with staff and others. Sharing expense report and timesheet.	$57.53
8/17/14	Clark	$45.00	2C	CM	*	4.75	communications	$213.75
8/17/14	Sievert	$38.35	2C	CM	*	1.50	Phone calls and emails with staff and others. .	$57.53
8/24/14	Clark	$45.00	2C	CM	*	.75	communications	$33.75
8/24/14	Sievert	$38.35	2C	CM	*	1.50	Phone calls and emails with staff and others.	$57.53		633.05
8/3/14	Clark	$45.00	2C	EM	*	3.25	research stamps for school events, order, proof posters	$146.25
8/3/14	Sievert	$38.35	2C	EM	*	7.00	Bike fleet summer maintenance. 10 new(used) bikes to replace the elementary fleet. Washed bikes. Stripped shifters/calbes and grips. Setup single-speed drivetrans. Aligned/replace brake pads.	$268.45
8/3/14	Sievert	$38.35	2C	EM	*	8.00	Continued ES bike fleet maintenance. Tightened/serviced cranks, cleaned drivetrains, removed stickers/tape, inventory needed parts and placed order using pricematch for lowest cost. Replaced rear deraileur and wheel. Replaced two chains. Replaced all grips. Inventory of serial numbers.	$306.80
8/10/14	Clark	$45.00	2C	EM	*	.50	Iwalk - give away supplies tracking	$22.50
8/10/14	Sievert	$38.35	2C	EM	*	6.50	Continued bike maintenance and relocating fleets. Replaced tires and tubes, check tires and rims for sharp spots or debris. Marked each bike with "I Stop @ Stop" stickers for identification. Delivered new ES fleet bikes to storage in Fairfax. Moved old ES fleet bikes to San Quentin. Looked for replacement canal bike. Pickup and return Uhaul truck.	$249.28
8/10/14	Sievert	$38.35	2C	EM	*	5.75	Reworked bike storage in trailer. Replaced 12 awkward metal hooks with 12 rubber bungees. Moved hooks to left side of trailer to hold pumps and other miscellaneious items. Added new bikes to fleet with rubber bungee hooks. Adapted bungees by shortening length and explored alternative hanging configurations. Continued annual maintenance. Stripped and ordered needed parts; brake pads, brake levers, calbes/housing, tires/tubes, and grips.	$220.51
8/17/14	Sievert	$38.35	2C	EM	*	7.50	Trailer maintenance and repair. Moved materials from trailer to tent. Cleaned and inspected floor-boards, sidewalls and roof. Removed trash and unused materials. Repaired leak from damaged sealant in roof panels. Refinished and repainted areas with rust. Reworked rubber hooks used to hang bicycles. Returned materials to trailer.	$287.63		1501.4125
8/3/14	Sievert	$38.35	2C	MT	*	2.75	Staff meeting with Peggy, Wendi, Gwen, Laura, and Lou.	$105.46
8/3/14	Sievert	$38.35	2C	MT	*	5.00	Staff retreat meeting with Wendi, Laura, Gwen, Peggy, Lou, and Jim. Covered education scheduling and program outlook for next year.	$191.75
8/10/14	Sievert	$38.35	2C	MT	*	1.50	All staff meeting with Wendi, Laura, Gwen, April, Alisha, Jim, April, Tom, and Andy.	$57.53
8/17/14	Clark	$45.00	2C	MT	*	1.50	staff meeting	$67.50
8/17/14	Sievert	$38.35	2C	MT	*	2.25	Staff meeting with Wendi, Peggy, Gwen, and Lou. Discussed plan for updating to K-5 and San Quentin (cans, bikes).	$86.29		508.525
7/27/14	Clark	$45.00	2C	SC	*	9.25	Update task list for school to contact, update calendar for 2014/15 school year.	$416.25
7/27/14	Sievert	$38.35	2C	SC	*	2.00	Starting to schedule the 2014-15 school year with Peggy. Discussed Davidson, Sun Valley, and Sinaloa. Email with Wendi as well regarding staff needs for Fridays and rodeos.	$76.70
8/3/14	Clark	$45.00	2C	SC	*	4.50	Scheduling- contact with schools, instructors, update calendar	$202.50
8/10/14	Kallins	$59.50	2C	SC	*	.50	recruiting rodeo helpers for the fall	$29.75
8/17/14	Clark	$45.00	2C	SC	*	15.00	scheduling: communications with staff, school contacts, updating calendar	$675.00
8/24/14	Clark	$45.00	2C	SC	*	1.50	scheduling: communications with staff, school contacts, updating calendar	$67.50	$6,580.95	1467.7
7/27/14	Kallins	$59.50	2D	CM	*	4.00	responding to general emails from public and staff	$238.00
7/27/14	Clark	$45.00	2D	CM	*	4.25	communications with staff and public	$191.25
8/3/14	Kallins	$59.50	2D	CM	*	7.00	responding to general emails	$416.50
8/3/14	Clark	$45.00	2D	CM	*	2.25	communications with staff and public	$101.25
8/10/14	Kallins	$59.50	2D	CM	*	4.00	responding to general emails	$238.00
8/10/14	Kallins	$59.50	2D	CM	*	1.00	respond to general emails	$59.50
8/17/14	Kallins	$59.50	2D	CM	*	5.00	responding to general emails from public and staff	$297.50
8/24/14	Kallins	$59.50	2D	CM	*	1.50	responding to general emails	$89.25		1631.25
7/27/14	Kallins	$59.50	2D	EV	*	4.00	preparations for fall walk to school days,	$238.00
7/27/14	Crawford	$31.00	2D	EV	*	1.00	spanish poster translations for iWalk	$31.00
8/3/14	Kallins	$59.50	2D	EV	*	3.00	posters and other incentives for	$178.50
8/10/14	Kelly	$43.55	2D	EV	*	1.00	iWalk - collaboration with Gwen	$43.55
8/17/14	Kallins	$59.50	2D	EV	*	3.50	conference call with State Health Dept on Iwalk; planning for team leader meeting; review and edit walk to school day check list and work with Laura on other materials	$208.25
8/17/14	Kelly	$43.55	2D	EV	*	14.00	RSVP calls for volunteer luncheon, nametags, Clif Kid coordination, hand stamps shipment, phone calls and emails, Sol Food order, created iWalk checklist 2014, created Bike Mobile document, carpool kit edits, meeting planning and organization, completed 35 shipping forms for Clif Kid	$609.70
8/17/14	Clark	$45.00	2D	EV	*	3.00	Iwalk prep supplies	$135.00
8/17/14	Sievert	$38.35	2D	EV	*	2.25	Bacich ES "Bike Build" with Principal Sally Peck and teaching staff. Helped check 8 bikes built to be given to the Canal Alliance. Gave short presentation to school staff regarding the services provided by Safe Routes.	$86.29
8/24/14	Kelly	$43.55	2D	EV	*	3.00	RSVP calls for volunteer luncheon, nametags, Clif Kid coordination, hand stamps shipment, phone calls and emails, Sol Food order, created iWalk checklist 2014, created Bike Mobile document, carpool kit edits, meeting planning and organization, completed 35 shipping forms for Clif Kid	$130.65
8/24/14	Kelly	$43.55	2D	EV	*	6.50	Team Leader prep meeting activities, documents and supplies coordination, packed car, Trader Joe's - flowers and fruit, final RSVPs, spreadsheet updates, emails and phone calls	$283.08
8/24/14	Clark	$45.00	2D	EV	*	3.25	Iwalk prep supplies	$146.25		2090.2625
8/10/14	Kelly	$43.55	2D	MT	*	6.00	Training and planning meeting at Venetia Valley School with Torhalla Dabalos, prep and follow-up, recuited two new parent leaders	$261.30		261.3
8/10/14	Kelly	$43.55	2D	PD	*	6.50	Stamp research and recommendations, placed order with Amazo for 30 kits, discussion with Wendi about projects and luncheon agenda, Clif Kid, SR2S and MCBC emails, team leader meeting planning, recruiting outreach and volunteer contact	$283.08
8/17/14	Kallins	$59.50	2D	PD	*	4.00	staff meeting plus prep - walk to school day, back to school, curriculum, type up notes. Talk to Laura about Clif kids order	$238.00		521.075
8/10/14	Kallins	$59.50	2D	VM	*	4.00	review eblast and agenda for team leader meeting; working with Laura on planning; carpool toolkit; other preparations for the start of the school year	$238.00
8/10/14	Kelly	$43.55	2D	VM	*	20.00	Design invitation for volunteer luncheon, created agenda for Team Leader meeting, Clif Kid shipment coordination, updated master supplies list, created check-list for Team Leader luncheon, volunteer outreach, SR2S and MCBC emails, Wendi - planning discussions, checklist for luncheon, coordination activities with Jeremy, carpool toolkit, recruiting outreach, back-to-school planning	$871.00
8/17/14	Kelly	$43.55	2D	VM	*	6.50	Contact with Principals, PTA Presidents, recruit new volunteers, volunteer communications --- phone calls and emails	$283.08
8/17/14	Clark	$45.00	2D	VM	*	1.25	Team Lead Meeting- shopping, prep supplies	$56.25
8/24/14	Kallins	$59.50	2D	VM	*	2.00	preparations for team leader meeting	$119.00
8/24/14	Clark	$45.00	2D	VM	*	2.00	Team Lead Meeting- prep supplies	$90.00		1657.325
8/3/14	Kallins	$59.50	2D	WR	*	2.00	work with Peggy on stamps, research and select options	$119.00
8/10/14	Kallins	$59.50	2D	WR	*	1.50	work with Laura on stamps for walk and roll Wednesdays; prep for team leader meeting	$89.25
8/24/14	Kelly	$43.55	2D	WR	*	1.50	Created eblast to Team Leaders about September 10 - Walk and Roll Wednesdays start day in Marin County - school newsletter submission	$65.33	$6,434.79	273.575
8/3/14	Froh	$43.00	2E	CM	*	.50	Communication with staff	$21.50
8/17/14	Froh	$43.00	2E	CM	*	1.50	Communication with staff	$64.50
8/17/14	Goodwin	$31.00	2E	CM	*	.50	Read and respond to emails.	$15.50
8/17/14	Goodwin	$31.00	2E	CM	*	.50	Phone conversation with Gwen re: staff meeting tomorrow, status of teen programing.	$15.50
8/24/14	Froh	$43.00	2E	CM	*	.50	Communication with staff.	$21.50		138.5
8/10/14	Goodwin	$31.00	2E	EV	*	1.50	emails to Sinaloa, Novato Police, Gwen, drafting email to announce iWalk.	$46.50		46.5
8/17/14	Froh	$43.00	2E	MT	*	1.50	Staff Meeting	$64.50
8/17/14	Goodwin	$31.00	2E	MT	*	1.50	SR2S Staff Meeting	$46.50		111
7/27/14	Froh	$43.00	2E	PD	*	.50	Communication with Lou; planning meetings	$21.50
8/3/14	Froh	$43.00	2E	PD	*	.50	Collaboration with Lou on fall rollout of events: iWalk bulletin notices	$21.50
8/10/14	Froh	$43.00	2E	PD	*	1.00	Collaboration on program development; iWalk and bulleting notices	$43.00
8/10/14	Goodwin	$31.00	2E	PD	*	2.50	Reading and Responding to emails, researching start dates of schools, planning out 1st school contact.	$77.50
8/17/14	Froh	$43.00	2E	PD	*	.50	Program Development; flyers	$21.50
8/17/14	Goodwin	$31.00	2E	PD	*	1.50	talk with Gwen re: giveaways for iWalk, teen program, reading and responding to emails.	$46.50
8/24/14	Froh	$43.00	2E	PD	*	4.50	Contacted schools about clubs and iWalk and dropped off posters.	$193.50	$721.00	425
7/27/14	Kallins	$59.50	2F	*	*	2.00	enter sutvey data	$119.00
7/27/14	Clark	$45.00	2F	*	*	1.75	Survey: update forms, update tracking, schedule tasks,	$78.75
8/3/14	Kallins	$59.50	2F	*	*	10.00	enter surveys into database; develop survey reports; transfer info to report cards	$595.00
8/3/14	Clark	$45.00	2F	*	*	1.00	Surveys- send to printer, pickup, start to sort supplies per school, plan for printing labels	$45.00
8/10/14	Kallins	$59.50	2F	*	*	8.00	report cards	$476.00
8/10/14	Kallins	$59.50	2F	*	*	2.00	survey analysis	$119.00
8/17/14	Kallins	$59.50	2F	*	*	1.00	create list of green schools	$59.50
8/17/14	Clark	$45.00	2F	*	*	2.25	survey prep materials	$101.25	$1,593.50	1593.5
8/3/14	Kallins	$59.50	3A	*	*	2.00	review carpool guide and send to Jeremy	$119.00
8/10/14	Kallins	$59.50	3A	*	*	1.00	meeting with new bi-lingual volunteer coordinator	$59.50
8/10/14	Kallins	$59.50	3A	*	*	1.00	work with Stephanie on strategies for promoting School Pool in Mill Valley	$59.50
8/17/14	Kallins	$59.50	3A	*	*	6.00	develop principal back to school email; work with KangaDo on flyer, review carpool toolkit; Cove web site updates; send out message to principals; develop Cove back to school materials research and update principals on database	$357.00	$595.00	595

						387.00			$17,972.61

## 4. Labor & Expenses by Task
Week Of	Staff	Rate	Task	Sub	School	Hours	Description	Cost

Task 1A: Labor
8/3/14	Kallins	$59.50	1A	GT	*	1.00	webinar on Sustainable communities program	$59.50
7/27/14	Kallins	$59.50	1A	RP	*	3.00	prepare invoice and reports	$178.50
8/3/14	Clark	$45.00	1A	RP	*	3.00	TAM Report- updating spread sheets, instructions	$135.00
8/10/14	Kallins	$59.50	1A	RP	*	1.00	staff time cards	$59.50
8/10/14	Kallins	$59.50	1A	RP	*	1.00	staff timecards	$59.50
8/17/14	Kallins	$59.50	1A	RP	*	.25	staff time cards	$14.88
8/24/14	Kallins	$59.50	1A	RP	*	1.50	staff time cards	$89.25
								$596.13
Task 1A: Expenses
							N/A	$0.00
								$0.00
Task 1A: Total
								$596.13

Task 1B: Labor
8/17/14	Kallins	$59.50	1B	*	*	6.00	attend meeting on Transit study, meet afterwards about specific information requests; research answers to information requests.	$357.00
								$357.00
Task 1B: Expenses
							N/A	$0.00
								$0.00
Task 1B: Total
								$357.00

Task 1D: Labor
7/27/14	Kallins	$59.50	1D	*	*	1.00	answer program questions from Alta	$59.50
8/10/14	Kallins	$59.50	1D	*	*	3.00	creative grant reporting	$178.50
								$238.00
Task 1D: Expenses
							N/A	$0.00
								$0.00
Task 1D: Total
								$238.00

Task 1F: Labor
8/3/14	Kallins	$59.50	1F	*	*	1.50	training for new blog site	$89.25
8/24/14	Kallins	$59.50	1F	*	*	1.00	finailize report cards	$59.50
								$148.75
Task 1F: Expenses
							N/A	$0.00
								$0.00
Task 1F: Total
								$148.75

Task 2A: Labor
8/3/14	Kallins	$59.50	2A	MT	*	1.00	help develop agenda for Hidden Valley, communications re: Kentfield task force meeting	$59.50
8/10/14	Kallins	$59.50	2A	MT	*	1.00	preparing for meetings for Hidden Valley, Kentfield	$59.50
8/10/14	Kallins	$59.50	2A	MT	*	3.50	Kentfield agenda; Hidden Valley meeting	$208.25
8/17/14	Kallins	$59.50	2A	MT	*	2.50	Kentfield Task Force meeting	$148.75
8/17/14	Clark	$45.00	2A	MT	KT	2.50	Task Force Meeting- Kentfield	$112.50
8/10/14	Kallins	$59.50	2A	TP	*	.50	revise Hidden Valley issues list	$29.75
8/17/14	Kallins	$59.50	2A	TP	*	1.50	travel plans on web site. Review Hidden Valley notes and issues list; provide info to SA Quality of life rep	$89.25
								$707.50
Task 2A: Expenses
							N/A	$0.00
								$0.00
Task 2A: Total
								$707.50

Task 2C: Labor
7/27/14	Sievert	$38.35	2C	CD	*	4.00	Continuing outline of K-5 comprehensive curriculum to facilitate block scheduling to increase effciency. Rough draft of 1st grade safety safari walk (non-street crossing) and partner sized vinyl mats to identify and discuss features of road design (signage .etc) and designated crossing structures (crosswalks, .etc).	$153.40
8/3/14	Sievert	$38.35	2C	CD	*	2.00	Researching transferring social media, news, and information into blog format and integration of constant contact and other media "blasts."	$76.70
8/3/14	Sievert	$38.35	2C	CD	*	6.00	Creating outline of more efficient block scheduling for the education programming in the schools. Developed alterntives to explore for each school and instrutor. Calculated efficiency based upon students hours/instructors hours/days required to travel. Created presentation for staff meeting.	$230.10
8/3/14	Sievert	$38.35	2C	CD	*	4.00	Revising outline of new K-5 comprehensive curriculum needed for efficienty education program scheduling. Reviewing Alameda K-5 curriculum. Evaluating materials costs for vinyl banners.	$153.40
8/10/14	Sievert	$38.35	2C	CD	*	6.75	Preparing education curriculum for 2014-15 academic year. Reworked bike rodeo to require 2 stations instead of 4 and potentially less paid instructors. Increased size of "Rules of the Road" to include up to 24 students. Folded "Cycling Circles" into "Obstacle Course" designed for up to 24 students. Added wide center lane with hazards (parked car, garbage can). Reorganized obstacles and circles to create flow of students that will not bottle-neck on teeter-totter by placing a start/stop location shortly before that feature. Created three sets of draft drawings before finding the best final design.	$258.86
8/10/14	Sievert	$38.35	2C	CD	*	7.00	Ressearch current products available and their design for chalking with sidewalk chalk. Chalk City product uses a stick with two foldable arms that hold chalk in a tube secured by rubber band material in center. Problems with hand chalkers include moving chalk as it wears down, securing chalk while maintaining ability to move it forward, and adding a weight to create solid lines over rough surface. Researched inner/outer diamter of PVC and common outer diamtere of chalk that we use. Designed a plunger stick to hold 1 piece of sidewalk chalk with a weight near the bottom to apply downward force. Outlined rainy-day back-up activities for K-3 curriculum to prevent rescheduling.	$268.45
8/10/14	Sievert	$38.35	2C	CD	*	5.00	Draft of 2014-15 handout for elementary PE teachers. Includes short description of lessons K-5 and description of new block scheduling. Lists general CA academic standards addressed, rainy-day alternatives and scheduling options. Formatted from 2013-14 elmentary teacher handout.	$191.75
8/10/14	Sievert	$38.35	2C	CD	*	5.75	Second and final draft of this years elementary handout explaining the new K-5 block scheduling. Highlighted benefits for teachers and both safety and health information for students at their school. Created a final PDF version shared with Peggy and staff for upcoming scheduling. Searched previously created listing of state education standards for K, 1, 3, and 5th grade.	$220.51
8/17/14	Kallins	$59.50	2C	CD	*	.75	review brief descriptions of new curruiculum line up. Sent out message to possible rodeo helpers	$44.63
8/17/14	Sievert	$38.35	2C	CD	*	6.50	K-5 curriculum: outlining matierals needed, review current visual aides, updated and shared curriculum overview for PE teachers, started creating basic procedures for individaul lesson plans, started draft of Stop, Look and Listen rhyme visual aid banner. Additional refinement of rodeo diagrams for dual station layout, noted additional instruction time due to single lesson (instead of three). Respond to feedback from Wendi and Lou regarding K-5 lessons.	$249.28
8/17/14	Sievert	$38.35	2C	CD	*	4.50	Edited new curriculum overview for teachers. Added sentence explaining new K-5 format. Edited SLL rhyme banner. Added graphics and reformated layout. Reviewed videos collected over past months for inclusion in "Drive that Bike" PowerPoint.	$172.58
8/17/14	Sievert	$38.35	2C	CD	*	5.25	Outlined schools to approach this year for K-5 curriclum with PE teachers and how many days would be required to visit. Revised scheduling for Davidson MS to include only 6 or 6/7 classes. Reviewed Arkansas mountain bike in school program for content that could be added to our rides. Reviewed past emails and contacted staff at San Quentin regarding application for a "vendor card" to access the bike program.	$201.34
8/24/14	Sievert	$38.35	2C	CD	*	6.50	Updating "Drive that Bike" PowerPoint for new academic year. Shortening number of slides, updating images and videos. Custom editing images and videos (cropping, resizing, editing for content and quality). Including more information placing bike rules in the context of shared rules amongst all road users. Checking animations and transitions for erros. Saving as PDF for presentation in case of PowerPoint failure. Sending copy to Gwen for review and comments.	$249.28
7/27/14	Sievert	$38.35	2C	CM	*	2.00	Phone calls and emails with staff and others.	$76.70
8/3/14	Sievert	$38.35	2C	CM	*	1.50	Phone calls and emails with staff and others.	$57.53
8/10/14	Clark	$45.00	2C	CM	*	.75	communications with staff and public	$33.75
8/10/14	Clark	$45.00	2C	CM	*	1.00	Communications- responding to emails	$45.00
8/10/14	Sievert	$38.35	2C	CM	*	1.50	Phone calls and emails with staff and others. Sharing expense report and timesheet.	$57.53
8/17/14	Clark	$45.00	2C	CM	*	4.75	communications	$213.75
8/17/14	Sievert	$38.35	2C	CM	*	1.50	Phone calls and emails with staff and others. .	$57.53
8/24/14	Clark	$45.00	2C	CM	*	.75	communications	$33.75
8/24/14	Sievert	$38.35	2C	CM	*	1.50	Phone calls and emails with staff and others.	$57.53
8/3/14	Clark	$45.00	2C	EM	*	3.25	research stamps for school events, order, proof posters	$146.25
8/3/14	Sievert	$38.35	2C	EM	*	7.00	Bike fleet summer maintenance. 10 new(used) bikes to replace the elementary fleet. Washed bikes. Stripped shifters/calbes and grips. Setup single-speed drivetrans. Aligned/replace brake pads.	$268.45
8/3/14	Sievert	$38.35	2C	EM	*	8.00	Continued ES bike fleet maintenance. Tightened/serviced cranks, cleaned drivetrains, removed stickers/tape, inventory needed parts and placed order using pricematch for lowest cost. Replaced rear deraileur and wheel. Replaced two chains. Replaced all grips. Inventory of serial numbers.	$306.80
8/10/14	Clark	$45.00	2C	EM	*	.50	Iwalk - give away supplies tracking	$22.50
8/10/14	Sievert	$38.35	2C	EM	*	6.50	Continued bike maintenance and relocating fleets. Replaced tires and tubes, check tires and rims for sharp spots or debris. Marked each bike with "I Stop @ Stop" stickers for identification. Delivered new ES fleet bikes to storage in Fairfax. Moved old ES fleet bikes to San Quentin. Looked for replacement canal bike. Pickup and return Uhaul truck.	$249.28
8/10/14	Sievert	$38.35	2C	EM	*	5.75	Reworked bike storage in trailer. Replaced 12 awkward metal hooks with 12 rubber bungees. Moved hooks to left side of trailer to hold pumps and other miscellaneious items. Added new bikes to fleet with rubber bungee hooks. Adapted bungees by shortening length and explored alternative hanging configurations. Continued annual maintenance. Stripped and ordered needed parts; brake pads, brake levers, calbes/housing, tires/tubes, and grips.	$220.51
8/17/14	Sievert	$38.35	2C	EM	*	7.50	Trailer maintenance and repair. Moved materials from trailer to tent. Cleaned and inspected floor-boards, sidewalls and roof. Removed trash and unused materials. Repaired leak from damaged sealant in roof panels. Refinished and repainted areas with rust. Reworked rubber hooks used to hang bicycles. Returned materials to trailer.	$287.63
8/3/14	Sievert	$38.35	2C	MT	*	2.75	Staff meeting with Peggy, Wendi, Gwen, Laura, and Lou.	$105.46
8/3/14	Sievert	$38.35	2C	MT	*	5.00	Staff retreat meeting with Wendi, Laura, Gwen, Peggy, Lou, and Jim. Covered education scheduling and program outlook for next year.	$191.75
8/10/14	Sievert	$38.35	2C	MT	*	1.50	All staff meeting with Wendi, Laura, Gwen, April, Alisha, Jim, April, Tom, and Andy.	$57.53
8/17/14	Clark	$45.00	2C	MT	*	1.50	staff meeting	$67.50
8/17/14	Sievert	$38.35	2C	MT	*	2.25	Staff meeting with Wendi, Peggy, Gwen, and Lou. Discussed plan for updating to K-5 and San Quentin (cans, bikes).	$86.29
7/27/14	Clark	$45.00	2C	SC	*	9.25	Update task list for school to contact, update calendar for 2014/15 school year.	$416.25
7/27/14	Sievert	$38.35	2C	SC	*	2.00	Starting to schedule the 2014-15 school year with Peggy. Discussed Davidson, Sun Valley, and Sinaloa. Email with Wendi as well regarding staff needs for Fridays and rodeos.	$76.70
8/3/14	Clark	$45.00	2C	SC	*	4.50	Scheduling- contact with schools, instructors, update calendar	$202.50
8/10/14	Kallins	$59.50	2C	SC	*	.50	recruiting rodeo helpers for the fall	$29.75
8/17/14	Clark	$45.00	2C	SC	*	15.00	scheduling: communications with staff, school contacts, updating calendar	$675.00
8/24/14	Clark	$45.00	2C	SC	*	1.50	scheduling: communications with staff, school contacts, updating calendar	$67.50
								$6,580.95
Task 2C: Expenses
							N/A	$0.00
								$0.00
Task 2C: Total
								$6,580.95

Task 2D: Labor
7/27/14	Kallins	$59.50	2D	CM	*	4.00	responding to general emails from public and staff	$238.00
7/27/14	Clark	$45.00	2D	CM	*	4.25	communications with staff and public	$191.25
8/3/14	Kallins	$59.50	2D	CM	*	7.00	responding to general emails	$416.50
8/3/14	Clark	$45.00	2D	CM	*	2.25	communications with staff and public	$101.25
8/10/14	Kallins	$59.50	2D	CM	*	4.00	responding to general emails	$238.00
8/10/14	Kallins	$59.50	2D	CM	*	1.00	respond to general emails	$59.50
8/17/14	Kallins	$59.50	2D	CM	*	5.00	responding to general emails from public and staff	$297.50
8/24/14	Kallins	$59.50	2D	CM	*	1.50	responding to general emails	$89.25
7/27/14	Kallins	$59.50	2D	EV	*	4.00	preparations for fall walk to school days,	$238.00
7/27/14	Crawford	$31.00	2D	EV	*	1.00	spanish poster translations for iWalk	$31.00
8/3/14	Kallins	$59.50	2D	EV	*	3.00	posters and other incentives for	$178.50
8/10/14	Kelly	$43.55	2D	EV	*	1.00	iWalk - collaboration with Gwen	$43.55
8/17/14	Kallins	$59.50	2D	EV	*	3.50	conference call with State Health Dept on Iwalk; planning for team leader meeting; review and edit walk to school day check list and work with Laura on other materials	$208.25
8/17/14	Kelly	$43.55	2D	EV	*	14.00	RSVP calls for volunteer luncheon, nametags, Clif Kid coordination, hand stamps shipment, phone calls and emails, Sol Food order, created iWalk checklist 2014, created Bike Mobile document, carpool kit edits, meeting planning and organization, completed 35 shipping forms for Clif Kid	$609.70
8/17/14	Clark	$45.00	2D	EV	*	3.00	Iwalk prep supplies	$135.00
8/17/14	Sievert	$38.35	2D	EV	*	2.25	Bacich ES "Bike Build" with Principal Sally Peck and teaching staff. Helped check 8 bikes built to be given to the Canal Alliance. Gave short presentation to school staff regarding the services provided by Safe Routes.	$86.29
8/24/14	Kelly	$43.55	2D	EV	*	3.00	RSVP calls for volunteer luncheon, nametags, Clif Kid coordination, hand stamps shipment, phone calls and emails, Sol Food order, created iWalk checklist 2014, created Bike Mobile document, carpool kit edits, meeting planning and organization, completed 35 shipping forms for Clif Kid	$130.65
8/24/14	Kelly	$43.55	2D	EV	*	6.50	Team Leader prep meeting activities, documents and supplies coordination, packed car, Trader Joe's - flowers and fruit, final RSVPs, spreadsheet updates, emails and phone calls	$283.08
8/24/14	Clark	$45.00	2D	EV	*	3.25	Iwalk prep supplies	$146.25
8/10/14	Kelly	$43.55	2D	MT	*	6.00	Training and planning meeting at Venetia Valley School with Torhalla Dabalos, prep and follow-up, recuited two new parent leaders	$261.30
8/10/14	Kelly	$43.55	2D	PD	*	6.50	Stamp research and recommendations, placed order with Amazo for 30 kits, discussion with Wendi about projects and luncheon agenda, Clif Kid, SR2S and MCBC emails, team leader meeting planning, recruiting outreach and volunteer contact	$283.08
8/17/14	Kallins	$59.50	2D	PD	*	4.00	staff meeting plus prep - walk to school day, back to school, curriculum, type up notes. Talk to Laura about Clif kids order	$238.00
8/10/14	Kallins	$59.50	2D	VM	*	4.00	review eblast and agenda for team leader meeting; working with Laura on planning; carpool toolkit; other preparations for the start of the school year	$238.00
8/10/14	Kelly	$43.55	2D	VM	*	20.00	Design invitation for volunteer luncheon, created agenda for Team Leader meeting, Clif Kid shipment coordination, updated master supplies list, created check-list for Team Leader luncheon, volunteer outreach, SR2S and MCBC emails, Wendi - planning discussions, checklist for luncheon, coordination activities with Jeremy, carpool toolkit, recruiting outreach, back-to-school planning	$871.00
8/17/14	Kelly	$43.55	2D	VM	*	6.50	Contact with Principals, PTA Presidents, recruit new volunteers, volunteer communications --- phone calls and emails	$283.08
8/17/14	Clark	$45.00	2D	VM	*	1.25	Team Lead Meeting- shopping, prep supplies	$56.25
8/24/14	Kallins	$59.50	2D	VM	*	2.00	preparations for team leader meeting	$119.00
8/24/14	Clark	$45.00	2D	VM	*	2.00	Team Lead Meeting- prep supplies	$90.00
8/3/14	Kallins	$59.50	2D	WR	*	2.00	work with Peggy on stamps, research and select options	$119.00
8/10/14	Kallins	$59.50	2D	WR	*	1.50	work with Laura on stamps for walk and roll Wednesdays; prep for team leader meeting	$89.25
8/24/14	Kelly	$43.55	2D	WR	*	1.50	Created eblast to Team Leaders about September 10 - Walk and Roll Wednesdays start day in Marin County - school newsletter submission	$65.33
								$6,434.79
Task 2D: Expenses
							N/A	$0.00
								$0.00
Task 2D: Total
								$6,434.79

Task 2E: Labor
8/3/14	Froh	$43.00	2E	CM	*	.50	Communication with staff	$21.50
8/17/14	Froh	$43.00	2E	CM	*	1.50	Communication with staff	$64.50
8/17/14	Goodwin	$31.00	2E	CM	*	.50	Read and respond to emails.	$15.50
8/17/14	Goodwin	$31.00	2E	CM	*	.50	Phone conversation with Gwen re: staff meeting tomorrow, status of teen programing.	$15.50
8/24/14	Froh	$43.00	2E	CM	*	.50	Communication with staff.	$21.50
8/10/14	Goodwin	$31.00	2E	EV	*	1.50	emails to Sinaloa, Novato Police, Gwen, drafting email to announce iWalk.	$46.50
8/17/14	Froh	$43.00	2E	MT	*	1.50	Staff Meeting	$64.50
8/17/14	Goodwin	$31.00	2E	MT	*	1.50	SR2S Staff Meeting	$46.50
7/27/14	Froh	$43.00	2E	PD	*	.50	Communication with Lou; planning meetings	$21.50
8/3/14	Froh	$43.00	2E	PD	*	.50	Collaboration with Lou on fall rollout of events: iWalk bulletin notices	$21.50
8/10/14	Froh	$43.00	2E	PD	*	1.00	Collaboration on program development; iWalk and bulleting notices	$43.00
8/10/14	Goodwin	$31.00	2E	PD	*	2.50	Reading and Responding to emails, researching start dates of schools, planning out 1st school contact.	$77.50
8/17/14	Froh	$43.00	2E	PD	*	.50	Program Development; flyers	$21.50
8/17/14	Goodwin	$31.00	2E	PD	*	1.50	talk with Gwen re: giveaways for iWalk, teen program, reading and responding to emails.	$46.50
8/24/14	Froh	$43.00	2E	PD	*	4.50	Contacted schools about clubs and iWalk and dropped off posters.	$193.50
								$721.00
Task 2E: Expenses
							N/A	$0.00
								$0.00
Task 2E: Total
								$721.00

Task 2F: Labor
7/27/14	Kallins	$59.50	2F	*	*	2.00	enter sutvey data	$119.00
7/27/14	Clark	$45.00	2F	*	*	1.75	Survey: update forms, update tracking, schedule tasks,	$78.75
8/3/14	Kallins	$59.50	2F	*	*	10.00	enter surveys into database; develop survey reports; transfer info to report cards	$595.00
8/3/14	Clark	$45.00	2F	*	*	1.00	Surveys- send to printer, pickup, start to sort supplies per school, plan for printing labels	$45.00
8/10/14	Kallins	$59.50	2F	*	*	8.00	report cards	$476.00
8/10/14	Kallins	$59.50	2F	*	*	2.00	survey analysis	$119.00
8/17/14	Kallins	$59.50	2F	*	*	1.00	create list of green schools	$59.50
8/17/14	Clark	$45.00	2F	*	*	2.25	survey prep materials	$101.25
								$1,593.50
Task 2F: Expenses
							N/A	$0.00
								$0.00
Task 2F: Total
								$1,593.50

Task 3A: Labor
8/3/14	Kallins	$59.50	3A	*	*	2.00	review carpool guide and send to Jeremy	$119.00
8/10/14	Kallins	$59.50	3A	*	*	1.00	meeting with new bi-lingual volunteer coordinator	$59.50
8/10/14	Kallins	$59.50	3A	*	*	1.00	work with Stephanie on strategies for promoting School Pool in Mill Valley	$59.50
8/17/14	Kallins	$59.50	3A	*	*	6.00	develop principal back to school email; work with KangaDo on flyer, review carpool toolkit; Cove web site updates; send out message to principals; develop Cove back to school materials research and update principals on database	$357.00
								$595.00
Task 3A: Expenses
							N/A	$0.00
								$0.00
Task 3A: Total
								$595.00

							Total Labor	$17,972.61
							Total Expenses	$0.00
						387.00
							Total Invoice	$17,972.61

## 5. Invoice Summary
Invoice for Services Provided by the Marin County Bicycle Coalition					Submit this Invoice to:		Parisi Transportation Consulting
for the Marin County Safe Routes to School Program					1750 Bridgeway, Suite B208
				Sausalito, CA 94965
Period: July 28-August 25, 2014
Date: September 23, 2014					Please Reference:		Project #13-013

		Labor Costs					Expense Costs

			Spent This	Previously	Total	Percent			Spent This	Previously	Total	Percent
Task		Budget	Period	Spent	Spent	Spent		Budget	Period	Spent	Spent	Spent

1A	Manage and Report Program	$25,800.00	$596.13	$18,682.23	$19,278.35	74.7%		n/a	n/a	n/a	n/a	n/a
1B	Coordinate with TAM programs	$2,135.00	$357.00	$1,998.04	$2,355.04	110.3%		n/a	n/a	n/a	n/a	n/a
1C	Stakeholder Outreach	$893.00	$0.00	$327.25	$327.25	36.6%		n/a	n/a	n/a	n/a	n/a
1D	Integrate Program Regionally	$4,638.00	$238.00	$13,390.06	$13,628.06	293.8%		n/a	n/a	n/a	n/a	n/a
1E	Establish Sustainable Funding	$0.00	$0.00	$33,609.92	$33,609.92	#DIV/0!		n/a	n/a	n/a	n/a	n/a
1F	Promote SR2S Program	$31,659.00	$148.75	$32,435.12	$32,583.87	102.9%		n/a	n/a	n/a	n/a	n/a

2A	Facilitate District Task Forces	$45,202.00	$707.50	$104,304.27	$105,011.77	232.3%		n/a	n/a	n/a	n/a	n/a
2B	Institutionalize the Program	$1,416.00	$0.00	$1,776.00	$1,776.00	125.4%		n/a	n/a	n/a	n/a	n/a
2C	Education	$226,734.00	$6,580.95	$265,370.27	$271,951.22	119.9%		n/a	n/a	n/a	n/a	n/a
2D	Encouragement	$121,085.00	$6,434.79	$95,125.36	$101,560.15	83.9%		n/a	n/a	n/a	n/a	n/a
2E	Organize Teen Clubs	$79,871.00	$721.00	$272,793.33	$273,514.33	342.4%		n/a	n/a	n/a	n/a	n/a
2F	Evaluate the Program	$15,126.00	$1,593.50	$87,004.47	$88,597.97	585.7%		n/a	n/a	n/a	n/a	n/a

3A	Promote SchoolPool Marin	$9,222.00	$565.25	$116,978.80	$117,544.05	1274.6%		n/a	n/a	n/a	n/a	n/a

Test seed	Test seeding a subtask	$0.00	$0.00	$0.00	$0.00	#DIV/0!		n/a	n/a	n/a	n/a	n/a

	Totals	$563,781.00	$17,942.86	$1,043,795.12	$1,061,737.98	188.3%		#REF!	#REF!	#REF!	#REF!	#REF!

1Task budgets shown are for 07/01/13 to 06/30/15

				Total Due This Period

I certify the amounts listed above have been properly incurred in the accomplishment of					Labor	$17,942.86
the services of this Contract (signature required). Attached is backup for this invoice.					Expenses	#REF!

				#REF!
This Invoice Includes the Following Documents:

1	Invoice Summary
2	Labor & Expenses by Task
3	Labor by Staff - Totaled
4	Timesheets (signatures required)
5	Receipts organized by task, for all expenses
6	Billing Codes
7	Progress Report